## Detailed Build Matrix
Component ID | Component Name | Assembly Stage | Planned Start Date | Planned Completion Date | Actual Start Date | Actual Completion Date | Resource Assigned | Dependency | Status
C-001 | Processor | Stage 1 | 2024-11-10 | 2024-11-20 | 2024-11-10 | 2024-11-20 | Team A | None | Completed
C-002 | Memory Module | Stage 2 | 2024-11-12 | 2024-11-22 | 2024-11-11 | 2024-11-21 | Team B | Processor | Ahead of Schedule
C-003 | Battery | Stage 3 | 2024-11-15 | 2024-11-28 | 2024-11-17 | Pending | Team C | Motherboard | Delayed
C-004 | Display Panel | Stage 2 | 2024-11-14 | 2024-11-25 | 2024-11-14 | Pending | Team B | Motherboard | In Progress
C-005 | Camera Module | Stage 3 | 2024-11-18 | 2024-12-01 | Pending | Pending | Team D | Display Panel | Not Started
C-006 | Motherboard | Stage 1 | 2024-11-10 | 2024-11-20 | 2024-11-10 | 2024-11-19 | Team A | None | Completed
C-007 | Cooling System | Stage 3 | 2024-11-20 | 2024-12-03 | Pending | Pending | Team C | Battery | Delayed
C-008 | Chassis | Stage 1 | 2024-11-09 | 2024-11-15 | 2024-11-09 | 2024-11-15 | Team A | None | Completed