## General Build Matrix
Component ID | Component Name | Assembly Stage | Start Date | Planned Completion Date | Actual Completion Date | Status
C-001 | Processor | Stage 1 | 2024-11-01 | 2024-11-10 | 2024-11-10 | Completed
C-002 | Memory Module | Stage 2 | 2024-11-05 | 2024-11-15 | 2024-11-14 | Completed
C-003 | Battery | Stage 3 | 2024-11-10 | 2024-11-20 | Pending | In Progress
C-004 | Display Panel | Stage 2 | 2024-11-07 | 2024-11-18 | Pending | In Progress
C-005 | Camera Module | Stage 3 | 2024-11-12 | 2024-11-25 | Pending | Not Started

## Vendor Status
Vendor Name | Component Supplied | Order Date | Delivery Date | Lead Time (Days) | Status
Vendor A | Processor | 2024-10-15 | 2024-10-28 | 13 | Delivered
Vendor B | Memory Module | 2024-10-17 | 2024-10-30 | 13 | Delivered
Vendor C | Battery | 2024-10-20 | 2024-11-05 | 16 | Delayed
Vendor D | Display Panel | 2024-10-18 | 2024-11-02 | 15 | On Track
Vendor E | Camera Module | 2024-10-22 | 2024-11-07 | 16 | On Track