## Build Matrix
Component ID | Component Name | Assembly Stage | Planned Completion Date | Actual Completion Date | Status
C-001 | Processor | Stage 1 | 2024-11-25 | 2024-11-25 | Completed
C-002 | Memory Module | Stage 2 | 2024-11-28 | 2024-11-27 | Ahead of Schedule
C-003 | Battery | Stage 3 | 2024-12-01 | Pending | Delayed
C-004 | Display Panel | Stage 2 | 2024-11-30 | Pending | In Progress
C-005 | Camera Module | Stage 3 | 2024-12-03 | Pending | In Progress

## Vendor Status
Vendor Name | Component Supplied | Lead Time (Days) | Delivery Date | Status
Vendor A | Processor | 15 | 2024-11-20 | Delivered
Vendor B | Memory Module | 10 | 2024-11-18 | Delivered
Vendor C | Battery | 20 | 2024-12-01 | Delayed
Vendor D | Display Panel | 12 | 2024-11-29 | On Track
Vendor E | Camera Module | 18 | 2024-12-02 | On Track