## Pilot Production Matrix
Build ID | Component/Assembly | Planned Start Date | Actual Start Date | Planned Completion Date | Actual Completion Date | Quality Check Status | Defect Rate (%) | Production Efficiency (%) | Status
P-001 | Processor Assembly | 2024-11-01 | 2024-11-01 | 2024-11-05 | 2024-11-04 | Passed | 1 | 95 | Completed
P-002 | Memory Module | 2024-11-03 | 2024-11-04 | 2024-11-08 | 2024-11-09 | Passed | 2 | 92 | Completed
P-003 | Battery Pack | 2024-11-05 | 2024-11-06 | 2024-11-10 | In Progress | Pending | - | - | Ongoing
P-004 | Display Panel | 2024-11-07 | Pending | 2024-11-12 | Pending | Pending | - | - | Not Started
P-005 | Camera Module | 2024-11-09 | Pending | 2024-11-14 | Pending | Pending | - | - | Not Started