## Risk Mitigation Matrix
Risk ID | Risk Description | Risk Category | Likelihood (1-5) | Impact (1-5) | Risk Level | Mitigation Strategy | Owner | Status
R-001 | Delay in raw material delivery | Supply Chain | 4 | 5 | High | Identify backup suppliers; negotiate shorter lead times | Procurement Team | Open
R-002 | Equipment breakdown in assembly | Manufacturing | 3 | 4 | Medium | Implement regular maintenance checks | Manufacturing Team | Open
R-003 | Vendor quality issues | Vendor Management | 2 | 5 | Medium | Conduct supplier audits and enforce quality checks | Quality Assurance | In Progress
R-004 | Design changes impacting production | Engineering | 3 | 3 | Medium | Apply strict change control process | Engineering Team | Open
R-005 | Labor shortages | Human Resources | 2 | 4 | Medium | Cross-train employees for critical roles | HR Team | Open
R-006 | Logistics disruption (weather) | Supply Chain | 4 | 3 | Medium | Develop alternative logistics routes | Logistics Team | Open
R-007 | Regulatory compliance delay | Compliance | 1 | 5 | Medium | Conduct early regulatory assessments | Compliance Team | Open
R-008 | Power outage at production facility | Infrastructure | 2 | 4 | Medium | Install backup generators | Operations Team | Planned