## Sheet1
Work Breakdown Structure (WBS) for Integrated NPI Build Optimization Framework
Task Number | Task Name | Start Date | End Date | Budget | Assigned Personnel
| Integrated NPI Build Optimization Framework | 2025-01-02 | 2026-09-06 | 566500
1 | Integrated NPI Build Optimization Framework WBS | 2025-01-02 | 2026-09-06 | 566500
1.1 | Project Initiation | 2025-01-02 | 2025-02-18 | 22500 | Project Manager, Project Sponsor
1.1.1 | Assign Project Manager | 2025-01-02 | 2025-01-03 | 0 | HR Team
1.1.2 | Receive Business Case | 2025-01-04 | 2025-01-05 | 0 | Project Sponsor
1.1.3 | Hold Kickoff Meeting | 2025-01-06 | 2025-01-07 | 0 | All Stakeholders
1.1.4 | Project Documentation | 2025-01-08 | 2025-02-17 | 22500 | Project Manager, PMO Team
1.1.4.1 | Project Charter | 2025-01-08 | 2025-01-12 | 2500 | Project Manager, Project Sponsor
1.1.4.1.1 | Create Project Charter | 2025-01-08 | 2025-01-09 | 1000 | Project Manager
1.1.4.1.1.1 | Executive Summary | 2025-01-08 | 2025-01-08 | 250 | Project Manager
1.1.4.1.1.2 | Business Need and Context | 2025-01-08 | 2025-01-08 | 250 | Project Manager
1.1.4.1.1.3 | Project Definition | 2025-01-08 | 2025-01-08 | 250 | Project Manager
1.1.4.1.1.4 | Risk Assessment | 2025-01-08 | 2025-01-09 | 250 | Project Manager
1.1.4.1.1.5 | Project Organization | 2025-01-09 | 2025-01-09 | 0 | Project Manager
1.1.4.1.2 | Final Draft of Project Charter | 2025-01-10 | 2025-01-11 | 1000 | Project Manager
1.1.4.1.3 | Initiate Team Meeting | 2025-01-12 | 2025-01-12 | 500 | All Stakeholders
1.1.4.2 | Business Case | 2025-01-13 | 2025-01-20 | 3000 | Project Manager
1.1.4.2.1 | Creation of Business Case | 2025-01-13 | 2025-01-18 | 2000 | Project Manager
1.1.4.2.1.1 | Executive Summary | 2025-01-13 | 2025-01-13 | 250 | Project Manager
1.1.4.2.1.2 | Businesss Need | 2025-01-13 | 2025-01-14 | 250 | Project Manager
1.1.4.2.1.3 | Objectives | 2025-01-14 | 2025-01-14 | 250 | Project Manager
1.1.4.2.1.4 | Feasibility Assessment | 2025-01-15 | 2025-01-15 | 250 | Project Manager
1.1.4.2.1.5 | Cost-Benefit Analysis | 2025-01-15 | 2025-01-16 | 250 | Project Manager
1.1.4.2.1.6 | Alternatives Considered | 2025-01-16 | 2025-01-16 | 250 | Project Manager
1.1.4.2.1.7 | Risks and Mitigation Strategies | 2025-01-17 | 2025-01-17 | 250 | Project Manager
1.1.4.2.1.8 | Project Timeline | 2025-01-17 | 2025-01-18 | 250 | Project Manager
1.1.4.2.2 | Document Business Case | 2025-01-18 | 2025-01-19 | 1000 | Project Manager
1.1.4.2.3 | Approve Business Case | 2025-01-20 | 2025-01-20 | 0 | Project Sponsor
1.1.4.3 | Feasibility Study | 2025-01-16 | 2025-01-21 | 2000 | Project Manager, Engineers
1.1.4.3.1 | Creation of Feasibility Study | 2025-01-16 | 2025-01-19 | 1000 | Project Manager, Engineers
1.1.4.3.1.1 | Technical Feasibility | 2025-01-16 | 2025-01-16 | 200 | Project Manager, Engineers
1.1.4.3.1.2 | Financial Feasibility | 2025-01-16 | 2025-01-17 | 200 | Project Manager, Engineers
1.1.4.3.1.3 | Operational Feasibility | 2025-01-17 | 2025-01-17 | 200 | Project Manager, Engineers
1.1.4.3.1.4 | Risk Analysis | 2025-01-18 | 2025-01-18 | 200 | Project Manager, Engineers
1.1.4.3.1.5 | Overall Feasibility | 2025-01-18 | 2025-01-19 | 200 | Project Manager, Engineers
1.1.4.3.2 | Document Feasibility Study | 2025-01-19 | 2025-01-20 | 1000 | Project Manager
1.1.4.3.3 | Approve Feasibility Study | 2025-01-21 | 2025-01-21 | 0 | Project Sponsor
1.1.4.4 | Stakeholder Register | 2025-01-22 | 2025-01-24 | 2000 | Project Manager
1.1.4.4.1 | Creation of Stakeholder Register | 2025-01-22 | 2025-01-22 | 1000 | Project Manager
1.1.4.4.2 | Document Stakeholder Register | 2025-01-22 | 2025-01-23 | 1000 | Project Manager
1.1.4.4.3 | Approve Stakeholder Register | 2025-01-24 | 2025-01-24 | 0 | Project Manager, Project Sponsor
1.1.4.5 | Risk Register (Premilinary) | 2025-01-25 | 2025-02-12 | 11000 | Risk Manager, Team Leads, Project Manager
1.1.4.5.1 | Identification | 2025-01-25 | 2025-02-01 | 7000 | Team Leads, Project Manager
1.1.4.5.1.1 | Brainstorm Risks | 2025-01-25 | 2025-01-29 | 5000 | Cross-Functional Teams
1.1.4.5.1.2 | Create Risk Register | 2025-01-30 | 2025-01-31 | 1000 | Risk Manager
1.1.4.5.1.3 | Document Risk Register | 2025-02-01 | 2025-02-02 | 1000 | Project Manager, Risk Manager
1.1.4.5.1.4 | Approve Risk Register | 2025-02-03 | 2025-02-03 | 0 | Project Sponsor
1.1.4.5.2 | Risk Analysis | 2025-02-02 | 2025-02-08 | 2000 | Risk Manager, Engineers
1.1.4.5.2.1 | Create Risk Analysis | 2025-02-02 | 2025-02-04 | 1000 | Project Manager, Risk Manager, Engineers
1.1.4.5.2.2 | Document Risk Analysis | 2025-02-05 | 2025-02-07 | 1000 | Project Manager
1.1.4.5.2.3 | Approve Risk Analysis | 2025-02-08 | 2025-02-08 | 0 | Project Sponsor
1.1.4.5.3 | Risk Prioritization | 2025-02-09 | 2025-02-12 | 2000 | Risk Manager, PMO Team
1.1.4.5.3.1 | Prioritze Risks | 2025-02-09 | 2025-02-09 | 1000 | Team Leads
1.1.4.5.3.2 | Document Prioritized Risks | 2025-02-10 | 2025-02-11 | 1000 | Project Manager
1.1.4.5.3.3 | Approve Risk Prioritization | 2025-02-12 | 2025-02-12 | 0 | Project Sponsor
1.1.4.6 | Assumptions Log | 2025-02-13 | 2025-02-17 | 2000 | PMO Team
1.1.4.6.1 | Creation of Assumptions log | 2025-02-13 | 2025-02-14 | 1000 | Project Manager
1.1.4.6.2 | Document Assumptions Log | 2025-02-15 | 2025-02-16 | 1000 | Project Manager
1.1.4.6.3 | Approve Assumptions Log | 2025-02-17 | 2025-02-17 | 0 | Project Sponsor
| Project Initiation Phase Complete | 2025-02-18 | 2025-02-18 | 0 | Project Manager
1.2 | Project Planning | 2025-02-23 | 2025-07-30 | 134000 | General Project Team
1.2.1 | Project Management Plan | 2025-02-23 | 2025-03-02 | 10500 | Project Manager, Project Sponsor
1.2.1.1 | Create Project Management Plan | 2025-02-23 | 2025-02-28 | 5500 | Project Manager, Project Sponsor
1.2.1.1.1 | Project Scope | 2025-02-23 | 2025-02-23 | 500 | Business Analyst, Project Manager
1.2.1.1.2 | Project Deliverables | 2025-02-23 | 2025-02-24 | 500 | General Project Team
1.2.1.1.3 | Project Milestones and Timeline | 2025-02-24 | 2025-02-24 | 500 | General Project Team
1.2.1.1.4 | Project Budget | 2025-02-24 | 2025-02-25 | 500 | Financial Analyst, Project Manager
1.2.1.1.5 | Budget Justification | 2025-02-25 | 2025-02-25 | 500 | Financial Analyst, Project Manager
1.2.1.1.6 | Project Resources | 2025-02-25 | 2025-02-26 | 500 | Resource Manager, HR Team
1.2.1.1.7 | Risk Management Plan | 2025-02-26 | 2025-02-26 | 500 | Risk Manager, Project Manager
1.2.1.1.8 | Communication Plan | 2025-02-26 | 2025-02-27 | 500 | Stakeholder Engagement Manager, Project Manager
1.2.1.1.9 | Quality Management Plan | 2025-02-27 | 2025-02-27 | 500 | Quality Assurance Engineer, Project Manager
1.2.1.1.10 | Change Management Plan | 2025-02-27 | 2025-02-28 | 500 | Change Manager, Project Manager
1.2.1.1.11 | Project Closure Plan | 2025-02-28 | 2025-02-28 | 500 | General Project Team
1.2.1.2 | Develop Project Management Plan | 2025-02-28 | 2025-03-01 | 5000 | Project Manager, Project Sponsor
1.2.1.3 | Approve Project Management Plan | 2025-03-02 | 2025-03-02 | 0 | Project Manager, Project Sponsor
1.2.2 | Scope Management Plan | 2025-03-03 | 2025-03-13 | 12500 | Business Analyst, Project Manager
1.2.2.1 | Create Scope Management Plan | 2025-03-03 | 2025-03-10 | 7500 | Business Analyst, Project Manager
1.2.2.1.1 | Business Requirements | 2025-03-03 | 2025-03-03 | 500 | Business Analyst, Project Manager
1.2.2.1.2 | Solution Requirements | 2025-03-03 | 2025-03-04 | 500 | Business Analyst, Project Manager
1.2.2.1.3 | Decide Scope Statement And Scope Baseline | 2025-03-04 | 2025-03-04 | 500 | Business Analyst, Project Manager
1.2.2.1.4 | MoSCoW Priortization Key | 2025-03-04 | 2025-03-05 | 500 | General Project Team
1.2.2.1.5 | Project Stakeholders | 2025-03-05 | 2025-03-05 | 500 | Stakeholder Engagement Manager, Business Analyst
1.2.2.1.6 | Available Resources | 2025-03-05 | 2025-03-06 | 500 | Resource Manager, HR Team
1.2.2.1.7 | In-scope Items | 2025-03-06 | 2025-03-06 | 500 | Business Analyst, Project Manager
1.2.2.1.8 | Out-of-scope Items | 2025-03-06 | 2025-03-07 | 500 | Business Analyst, Project Manager
1.2.2.1.9 | Project Deliverables | 2025-03-07 | 2025-03-07 | 500 | General Project Team
1.2.2.1.10 | Project Milestones | 2025-03-07 | 2025-03-08 | 500 | General Project Team
1.2.2.1.11 | Key Notes | 2025-03-08 | 2025-03-08 | 500 | General Project Team
1.2.2.1.12 | Project Constraints | 2025-03-08 | 2025-03-09 | 500 | General Project Team
1.2.2.1.13 | Project Assumptions | 2025-03-09 | 2025-03-09 | 500 | General Project Team
1.2.2.1.14 | Acceptance Criteria | 2025-03-09 | 2025-03-10 | 500 | General Project Team
1.2.2.1.15 | Project Boundaries | 2025-03-10 | 2025-03-10 | 500 | General Project Team
1.2.2.2 | Develop Scope Management Plan | 2025-03-11 | 2025-03-12 | 5000 | Business Analyst, Project Manager
1.2.2.3 | Approve Scope Management Plan | 2025-03-13 | 2025-03-13 | 0 | Business Analyst, Project Manager
1.2.3 | Requirements Management Plan | 2025-03-14 | 2025-05-09 | 22500 | Business Analyst, Project Manager
1.2.3.1 | Create Requirements Management Plan | 2025-03-14 | 2025-05-06 | 17500 | Business Analyst, Project Manager
1.2.3.1.1 | Requirements Identification | 2025-03-14 | 2025-03-14 | 500 | Business Analyst, Project Manager
1.2.3.1.2 | Requirements Priortization | 2025-03-14 | 2025-03-15 | 500 | Business Analyst, Project Manager
1.2.3.1.3 | Requirements Change Management | 2025-03-15 | 2025-03-15 | 500 | Business Analyst, Project Manager
1.2.3.1.4 | Requirements Validation And Verification | 2025-03-16 | 2025-03-16 | 500 | Business Analyst, Project Manager
1.2.3.1.5 | Tools And Techniques | 2025-03-16 | 2025-03-17 | 500 | General Project Team
1.2.3.1.6 | Requirements Traceability Matrix | 2025-03-17 | 2025-05-06 | 15000 | Business Analyst, Project Manager
1.2.3.1.6.1 | Centralized NPI Dashboard Matrix | 2025-03-17 | 2025-03-21 | 1500 | General Project Team
1.2.3.1.6.1.1 | Create Centralized NPI Dashboard Matrix | 2025-03-17 | 2025-03-18 | 500 | General Project Team
1.2.3.1.6.1.2 | Develop Centralized NPI Dashboard Matrix | 2025-03-19 | 2025-03-20 | 1000 | General Project Team
1.2.3.1.6.1.3 | Approve Centralized NPI Dashboard Matrix | 2025-03-21 | 2025-03-21 | 0 | General Project Team
1.2.3.1.6.2 | Automated BOM Management Matrix | 2025-03-22 | 2025-03-26 | 1500 | General Project Team
1.2.3.1.6.2.1 | Create Automated BOM Management Matrix | 2025-03-22 | 2025-03-23 | 500 | General Project Team
1.2.3.1.6.2.2 | Develop Automated BOM Management Matrix | 2025-03-24 | 2025-03-25 | 1000 | General Project Team
1.2.3.1.6.2.3 | Approve Automated BOM Management Matrix | 2025-03-26 | 2025-03-26 | 0 | General Project Team
1.2.3.1.6.3 | Vendor Collaboration Tool Matrix | 2025-03-27 | 2025-03-31 | 1500 | General Project Team
1.2.3.1.6.3.1 | Create Vendor Collaboration Tool Matrix | 2025-03-27 | 2025-03-28 | 500 | General Project Team
1.2.3.1.6.3.2 | Develop Vendor Collaboration Tool Matrix | 2025-03-29 | 2025-03-30 | 1000 | General Project Team
1.2.3.1.6.3.3 | Approve Vendor Collaboration Tool Matrix | 2025-03-31 | 2025-03-31 | 0 | General Project Team
1.2.3.1.6.4 | Risk Mitigation Framework For Prodiction Delays Matrix | 2025-04-01 | 2025-04-05 | 1500 | Risk Manager, Project Manager
1.2.3.1.6.4.1 | Create Risk Mitigation Framework For Prodiction Delays Matrix | 2025-04-01 | 2025-04-02 | 500 | Risk Manager, Project Manager
1.2.3.1.6.4.2 | Develop Risk Mitigation Framework For Prodiction Delays Matrix | 2025-04-03 | 2025-04-04 | 1000 | Risk Manager, Project Manager
1.2.3.1.6.4.3 | Approve Risk Mitigation Framework For Prodiction Delays Matrix | 2025-04-05 | 2025-04-05 | 0 | Risk Manager, Project Manager
1.2.3.1.6.5 | Material Forecasting Tool For Production Scheduling Matrix | 2025-04-06 | 2025-04-10 | 1500 | General Project Team
1.2.3.1.6.5.1 | Create Material Forecasting Tool For Production Scheduling Matrix | 2025-04-06 | 2025-04-07 | 500 | General Project Team
1.2.3.1.6.5.2 | Develop Material Forecasting Tool For Production Scheduling Matrix | 2025-04-08 | 2025-04-09 | 1000 | General Project Team
1.2.3.1.6.5.3 | Approve Material Forecasting Tool For Production Scheduling Matrix | 2025-04-10 | 2025-04-10 | 0 | General Project Team
1.2.3.1.6.6 | Conduct Pilot Production Runs For Manufacturing Readiness Matrix | 2025-04-11 | 2025-04-15 | 1500 | General Project Team
1.2.3.1.6.6.1 | Create Conduct Pilot Production Runs For Manufacturing Readiness Matrix | 2025-04-11 | 2025-04-12 | 500 | General Project Team
1.2.3.1.6.6.2 | Develop Conduct Pilot Production Runs For Manufacturing Readiness Matrix | 2025-04-13 | 2025-04-14 | 1000 | General Project Team
1.2.3.1.6.6.3 | Approve Conduct Pilot Production Runs For Manufacturing Readiness Matrix | 2025-04-15 | 2025-04-15 | 0 | General Project Team
1.2.3.1.6.7 | Automated Quality Check Matrix | 2025-04-16 | 2025-04-20 | 1500 | Quality Assurance Engineer, Project Manager
1.2.3.1.6.7.1 | Create Automated Quality Check Matrix | 2025-04-16 | 2025-04-17 | 500 | Quality Assurance Engineer, Project Manager
1.2.3.1.6.7.2 | Develop Automated Quality Check Matrix | 2025-04-18 | 2025-04-19 | 1000 | Quality Assurance Engineer, Project Manager
1.2.3.1.6.7.3 | Approve Automated Quality Check Matrix | 2025-04-20 | 2025-04-20 | 0 | Quality Assurance Engineer, Project Manager
1.2.3.1.6.8 | Predictive Analysis Matrix | 2025-04-21 | 2025-04-25 | 1500 | General Project Team
1.2.3.1.6.8.1 | Create Predictive Analysis Matrix | 2025-04-21 | 2025-04-22 | 500 | General Project Team
1.2.3.1.6.8.2 | Develop Predictive Analysis Matrix | 2025-04-23 | 2025-04-24 | 1000 | General Project Team
1.2.3.1.6.8.3 | Approve Predictive Anaylsis Matrix | 2025-04-25 | 2025-04-25 | 0 | General Project Team
1.2.3.1.6.9 | Industry Regulations Matrix | 2025-04-26 | 2025-04-30 | 1500 | General Project Team
1.2.3.1.6.9.1 | Create Industry Regulations Matrix | 2025-04-26 | 2025-04-27 | 500 | General Project Team
1.2.3.1.6.9.2 | Develop Industry Regulations Matrix | 2025-04-28 | 2025-04-29 | 1000 | General Project Team
1.2.3.1.6.9.3 | Approve Industry Regulations Matrix | 2025-04-30 | 2025-04-30 | 0 | General Project Team
1.2.3.1.6.10 | Final Documentation and Presentation Matrix | 2025-05-01 | 2025-05-06 | 1500 | General Project Team
1.2.3.1.6.10.1 | Create Final Documentation and Presentation Matrix | 2025-05-02 | 2025-05-03 | 500 | General Project Team
1.2.3.1.6.10.2 | Develop Final Documentation and Presentation Matrix | 2025-05-04 | 2025-05-05 | 1000 | General Project Team
1.2.3.1.6.10.3 | Approve Final Documentation and Presentation Matrix | 2025-05-06 | 2025-05-06 | 0 | General Project Team
1.2.3.2 | Develop Requirements Management Plan | 2025-05-07 | 2025-05-08 | 5000 | Business Analyst, Project Manager
1.2.3.3 | Approve Requirements Management Plan | 2025-05-09 | 2025-05-09 | 0 | Business Analyst, Project Manager
1.2.4 | Schedule Management Plan | 2025-05-10 | 2025-05-17 | 9000 | Project Scheduler, Project Manager
1.2.4.1 | Create Schedule Management Plan | 2025-05-10 | 2025-05-14 | 4000 | Project Scheduler, Project Manager
1.2.4.1.1 | Schedule Development Process | 2025-05-10 | 2025-05-10 | 1000 | Project Scheduler, Project Manager
1.2.4.1.2 | Project Schedule (Milestones and Timelines) | 2025-05-10 | 2025-05-11 | 500 | Project Scheduler, Project Manager
1.2.4.1.3 | Schedule Control Process | 2025-05-11 | 2025-05-11 | 500 | Project Scheduler, Project Manager
1.2.4.1.4 | Tools And Techniques | 2025-05-12 | 2025-05-12 | 500 | General Project Team
1.2.4.1.5 | Schedule Risks And Mitigation | 2025-05-12 | 2025-05-13 | 500 | Project Scheduler, Project Manager
1.2.4.1.6 | Performance Monitoring | 2025-05-13 | 2025-05-13 | 500 | General Project Team
1.2.4.1.7 | Reporting And Communication | 2025-05-14 | 2025-05-14 | 500 | Stakeholder Engagement Manager, Project Manager
1.2.4.2 | Develop Schedule Management Plan | 2025-05-15 | 2025-05-16 | 5000 | Project Scheduler, Project Manager
1.2.4.3 | Approve Schedule Management Plan | 2025-05-17 | 2025-05-17 | 0 | Project Scheduler, Project Manager
1.2.5 | Cost Management Plan | 2025-05-18 | 2025-05-25 | 8500 | Financial Analyst, Project Manager
1.2.5.1 | Create Cost Management Plan | 2025-05-18 | 2025-05-22 | 3500 | Financial Analyst, Project Manager
1.2.5.1.1 | Cost Estimation | 2025-05-18 | 2025-05-18 | 500 | Financial Analyst, Project Manager
1.2.5.1.2 | Budget Breakdown | 2025-05-18 | 2025-05-19 | 500 | Financial Analyst, Project Manager
1.2.5.1.3 | Cost Control Process | 2025-05-19 | 2025-05-19 | 500 | Financial Analyst, Project Manager
1.2.5.1.4 | Earned Value Management | 2025-05-20 | 2025-05-20 | 500 | General Project Team
1.2.5.1.5 | Cost Reporting | 2025-05-20 | 2025-05-21 | 500 | Financial Analyst, Project Manager
1.2.5.1.6 | Cost Control For Budget Adjustments | 2025-05-21 | 2025-05-21 | 500 | Financial Analyst, Project Manager
1.2.5.1.7 | Risk And Contingency Management | 2025-05-21 | 2025-05-22 | 500 | Risk Manager, Project Manager
1.2.5.2 | Develop Cost Management Plan | 2025-05-23 | 2025-05-24 | 5000 | Financial Analyst, Project Manager
1.2.5.3 | Approve Cost Management Plan | 2025-05-25 | 2025-05-25 | 0 | Financial Analyst, Project Manager
1.2.6 | Resource Management Plan | 2025-05-26 | 2025-06-04 | 9500 | Resource Manager, HR Team
1.2.6.1 | Create Resource Management Plan | 2025-05-26 | 2025-06-01 | 4500 | Resource Manager, HR Team
1.2.6.1.1 | Resource Identification | 2025-05-26 | 2025-05-27 | 1000 | Resource Manager, HR Team
1.2.6.1.1.1 | Human Resources | 2025-05-26 | 2025-05-26 | 500 | Resource Manager, HR Team
1.2.6.1.1.2 | Material And Equipment Resources | 2025-05-27 | 2025-05-27 | 500 | Resource Manager, HR Team
1.2.6.1.2 | Resource Acquisition | 2025-05-28 | 2025-05-28 | 500 | Resource Manager, HR Team
1.2.6.1.3 | Resource Allocation and Scheduling | 2025-05-28 | 2025-05-29 | 500 | Resource Manager, HR Team
1.2.6.1.4 | Resource Monitoring and Control | 2025-05-29 | 2025-05-29 | 500 | Resource Manager, HR Team
1.2.6.1.5 | Conflict Resolution | 2025-05-30 | 2025-05-30 | 500 | General Project Team
1.2.6.1.6 | Resource Risk Management | 2025-05-30 | 2025-05-31 | 500 | Resource Manager, HR Team
1.2.6.1.7 | Resource Release Plan | 2025-05-31 | 2025-05-31 | 500 | Resource Manager, HR Team
1.2.6.1.8 | Resource Reporting | 2025-06-01 | 2025-06-01 | 500 | Resource Manager, HR Team
1.2.6.2 | Develop Resource Management Plan | 2025-06-02 | 2025-06-03 | 5000 | Resource Manager, HR Team
1.2.6.3 | Approve Resource Management Plan | 2025-06-04 | 2025-06-04 | 0 | Resource Manager, HR Team
1.2.7 | Risk Management Plan | 2025-06-05 | 2025-06-11 | 8500 | Risk Manager, Project Manager
1.2.7.1 | Create Risk Management Plan | 2025-06-05 | 2025-06-09 | 3500 | Risk Manager, Project Manager
1.2.7.1.1 | Determine Risk Management Process | 2025-06-05 | 2025-06-05 | 500 | Risk Manager, Project Manager
1.2.7.1.2 | Determine Risk Categories | 2025-06-05 | 2025-06-06 | 500 | Risk Manager, Project Manager
1.2.7.1.3 | Develop Risk Register (Category) | 2025-06-06 | 2025-06-06 | 500 | Risk Manager, Project Manager
1.2.7.1.4 | Risk Probability and Impact Matrix | 2025-06-07 | 2025-06-07 | 500 | Risk Manager, Project Manager
1.2.7.1.5 | Risk Response Strategies | 2025-06-07 | 2025-06-08 | 500 | Risk Manager, Project Manager
1.2.7.1.6 | Risk Monitoring and Reporting | 2025-06-08 | 2025-06-08 | 500 | Risk Manager, Project Manager
1.2.7.1.7 | Contingency and Reserve Planning | 2025-06-09 | 2025-06-09 | 500 | General Project Team
1.2.7.2 | Develop Risk Management Plan | 2025-06-10 | 2025-06-10 | 5000 | Risk Manager, Project Manager
1.2.7.3 | Approve Risk Management Plan | 2025-06-11 | 2025-06-11 | 0 | Risk Manager, Project Manager
1.2.8 | Communication Management Plan | 2025-06-12 | 2025-06-17 | 8000 | Stakeholder Engagement Manager, Project Manager
1.2.8.1 | Create Communication Management Plan | 2025-06-12 | 2025-06-15 | 3000 | Stakeholder Engagement Manager, Project Manager
1.2.8.1.1 | Identify Stakeholder Communication Requirements | 2025-06-12 | 2025-06-12 | 500 | Business Analyst, Project Manager
1.2.8.1.2 | Communication Methods And Tools | 2025-06-12 | 2025-06-13 | 500 | Stakeholder Engagement Manager, Project Manager
1.2.8.1.3 | Communication Frequency and Schedule | 2025-06-13 | 2025-06-13 | 500 | Project Scheduler, Project Manager
1.2.8.1.4 | Escalation Process | 2025-06-14 | 2025-06-14 | 500 | General Project Team
1.2.8.1.5 | Change Communication Management | 2025-06-14 | 2025-06-15 | 500 | Stakeholder Engagement Manager, Project Manager
1.2.8.1.6 | Communication Performance Measurement | 2025-06-15 | 2025-06-15 | 500 | Stakeholder Engagement Manager, Project Manager
1.2.8.2 | Develop Communication Management Plan | 2025-06-16 | 2025-06-16 | 5000 | Stakeholder Engagement Manager, Project Manager
1.2.8.3 | Approve Communication Management Plan | 2025-06-17 | 2025-06-17 | 0 | Stakeholder Engagement Manager, Project Manager
1.2.9 | Procurement Management Plan | 2025-06-18 | 2025-06-26 | 9000 | Procurement Specialist, Project Manager
1.2.9.1 | Create Procurement Management Plan | 2025-06-18 | 2025-06-23 | 4000 | Procurement Specialist, Project Manager
1.2.9.1.1 | Identify Procurement Requirements | 2025-06-18 | 2025-06-18 | 500 | Business Analyst, Project Manager
1.2.9.1.2 | Procurement Process | 2025-06-18 | 2025-06-19 | 500 | Procurement Specialist, Project Manager
1.2.9.1.3 | Vendor Evaluation and Selection Criteria | 2025-06-19 | 2025-06-19 | 500 | General Project Team
1.2.9.1.4 | Contract Types | 2025-06-20 | 2025-06-20 | 500 | General Project Team
1.2.9.1.5 | Procurement Risk Management | 2025-06-20 | 2025-06-21 | 500 | Risk Manager, Project Manager
1.2.9.1.6 | Procurement Monitoring and Control | 2025-06-21 | 2025-06-21 | 500 | Procurement Specialist, Project Manager
1.2.9.1.7 | Payment Terms and Invoicing | 2025-06-22 | 2025-06-22 | 500 | General Project Team
1.2.9.1.8 | Contract Closure | 2025-06-22 | 2025-06-23 | 500 | General Project Team
1.2.9.2 | Develop Procurement Management Plan | 2025-06-24 | 2025-06-25 | 5000 | Procurement Specialist, Project Manager
1.2.9.3 | Approve Procurement Management Plan | 2025-06-26 | 2025-06-26 | 0 | Procurement Specialist, Project Manager
1.2.10 | Quality Management Plan | 2025-06-27 | 2025-07-05 | 9500 | Quality Assurance Engineer, Project Manager
1.2.10.1 | Create Quality Management Plan | 2025-06-27 | 2025-07-02 | 4500 | Quality Assurance Engineer, Project Manager
1.2.10.1.1 | Determine Quality Standards | 2025-06-27 | 2025-06-27 | 500 | Quality Assurance Engineer, Project Manager
1.2.10.1.2 | Quality Assurance Activities | 2025-06-27 | 2025-06-28 | 500 | Quality Assurance Engineer, Project Manager
1.2.10.1.3 | Quality Control Activities | 2025-06-28 | 2025-06-28 | 500 | Quality Assurance Engineer, Project Manager
1.2.10.1.4 | Quality Metrics | 2025-06-29 | 2025-06-29 | 500 | Quality Assurance Engineer, Project Manager
1.2.10.1.5 | Quality Control Tools and Techniques | 2025-06-29 | 2025-06-30 | 500 | Quality Assurance Engineer, Project Manager
1.2.10.1.6 | Continuous Improvement Process | 2025-06-30 | 2025-06-30 | 500 | General Project Team
1.2.10.1.7 | Quality Issue Escalation Process | 2025-07-01 | 2025-07-01 | 500 | Quality Assurance Engineer, Project Manager
1.2.10.1.8 | Quality Audits and Reviews | 2025-07-01 | 2025-07-02 | 500 | Quality Assurance Engineer, Project Manager
1.2.10.1.9 | Corrective and Preventive Actions | 2025-07-02 | 2025-07-02 | 500 | General Project Team
1.2.10.2 | Develop Quality Management Plan | 2025-07-03 | 2025-07-04 | 5000 | Quality Assurance Engineer, Project Manager
1.2.10.3 | Approve Quality Management Plan | 2025-07-05 | 2025-07-05 | 0 | Quality Assurance Engineer, Project Manager
1.2.11 | Change Management Plan | 2025-07-06 | 2025-07-14 | 9500 | Change Manager, Project Manager
1.2.11.1 | Create Change Management Plan | 2025-07-06 | 2025-07-11 | 4500 | Change Manager, Project Manager
1.2.11.1.1 | Create Change Management Process | 2025-07-06 | 2025-07-06 | 500 | Change Manager, Project Manager
1.2.11.1.2 | Create Change Management Form Template | 2025-07-06 | 2025-07-07 | 500 | Change Manager, Project Manager
1.2.11.1.3 | Change Impact Analysis | 2025-07-07 | 2025-07-07 | 500 | General Project Team
1.2.11.1.4 | Change Approval Levels | 2025-07-08 | 2025-07-08 | 500 | General Project Team
1.2.11.1.5 | Change Control Board | 2025-07-08 | 2025-07-09 | 500 | General Project Team
1.2.11.1.6 | Change Tracking and Monitoring | 2025-07-09 | 2025-07-09 | 500 | General Project Team
1.2.11.1.7 | Change Log Template | 2025-07-10 | 2025-07-10 | 500 | General Project Team
1.2.11.1.8 | Change Communication Strategy | 2025-07-10 | 2025-07-11 | 500 | Stakeholder Engagement Manager, Project Manager
1.2.11.1.9 | Risk Management For Changes | 2025-07-11 | 2025-07-11 | 500 | Risk Manager, Project Manager
1.2.11.2 | Develop Change Management Plan | 2025-07-12 | 2025-07-13 | 5000 | Change Manager, Project Manager
1.2.11.3 | Approve Change Management Plan | 2025-07-14 | 2025-07-14 | 0 | Change Manager, Project Manager
1.2.12 | Stakeholder Engagement Plan | 2025-07-15 | 2025-07-22 | 8500 | Stakeholder Engagement Manager, Business Analyst
1.2.12.1 | Create Stakeholder Engagement Plan | 2025-07-15 | 2025-07-19 | 3500 | Stakeholder Engagement Manager, Business Analyst
1.2.12.1.1 | Stakeholder Identification And Analysis | 2025-07-15 | 2025-07-15 | 500 | Stakeholder Engagement Manager, Business Analyst
1.2.12.1.2 | Stakeholder Enagement Matrix | 2025-07-15 | 2025-07-16 | 500 | Stakeholder Engagement Manager, Business Analyst
1.2.12.1.3 | Stakeholder Communication Plan | 2025-07-16 | 2025-07-16 | 500 | Stakeholder Engagement Manager, Project Manager
1.2.12.1.4 | Engagement Strategies | 2025-07-17 | 2025-07-17 | 500 | General Project Team
1.2.12.1.5 | Stakeholder Engagement Monitoring | 2025-07-17 | 2025-07-18 | 500 | Stakeholder Engagement Manager, Business Analyst
1.2.12.1.6 | Stakeholder Issue Resolution Process | 2025-07-18 | 2025-07-18 | 500 | Stakeholder Engagement Manager, Business Analyst
1.2.12.1.7 | Change Management For Stakeholder Engagement | 2025-07-19 | 2025-07-19 | 500 | Change Manager, Project Manager
1.2.12.2 | Develop Stakeholder Engagement Plan | 2025-07-20 | 2025-07-21 | 5000 | Stakeholder Engagement Manager, Business Analyst
1.2.12.3 | Approve Stakeholder Engagement Plan | 2025-07-22 | 2025-07-22 | 0 | Stakeholder Engagement Manager, Business Analyst
1.2.13 | Budget Management Plan | 2025-07-23 | 2025-07-30 | 8500 | Financial Analyst, Project Manager
1.2.13.1 | Create Budget Management Plan | 2025-07-23 | 2025-07-27 | 3500 | Financial Analyst, Project Manager
1.2.13.1.1 | Budget Breakdown | 2025-07-23 | 2025-07-23 | 500 | Financial Analyst, Project Manager
1.2.13.1.2 | Cost Estimation Methods | 2025-07-23 | 2025-07-24 | 500 | Financial Analyst, Project Manager
1.2.13.1.3 | Cost Control And Monitoring | 2025-07-24 | 2025-07-24 | 500 | Financial Analyst, Project Manager
1.2.13.1.4 | Cost Performance Metrics | 2025-07-25 | 2025-07-25 | 500 | Financial Analyst, Project Manager
1.2.13.1.5 | Funding And Payment Schedule | 2025-07-25 | 2025-07-26 | 500 | Project Scheduler, Project Manager
1.2.13.1.6 | Risk Management And Contingency Planning | 2025-07-26 | 2025-07-26 | 500 | Risk Manager, Project Manager
1.2.13.1.7 | Budget Change Control Process | 2025-07-27 | 2025-07-27 | 500 | Financial Analyst, Project Manager
1.2.13.2 | Develop Budget Management Plan | 2025-07-28 | 2025-07-29 | 5000 | Financial Analyst, Project Manager
1.2.13.3 | Approve Budget Management Plan | 2025-07-30 | 2025-07-30 | 0 | Financial Analyst, Project Manager
| Project Planning Phase Complete | 2025-07-30 | 2025-07-30 | 0 | General Project Team
1.3 | Project Execution | 2025-07-31 | 2026-05-03 | 256000 | General Project Team
1.3.1 | Design | 2025-07-31 | 2025-08-11 | 7500 | General Project Team
1.3.1.1 | Create Design Prototype | 2025-07-31 | 2025-08-06 | 1500 | General Project Team
1.3.1.2 | Present Design Prototype to Project Sponsor | 2025-08-07 | 2025-08-08 | 1500 | General Project Team
1.3.1.3 | Approve Design Prototype | 2025-08-09 | 2025-08-09 | 1500 | General Project Team
1.3.1.4 | Design Prototype Complete | 2025-08-10 | 2025-08-10 | 1500 | General Project Team
1.3.1.5 | Design Complete | 2025-08-11 | 2025-08-11 | 1500 | General Project Team
1.3.2 | Procurement Management Plan | 2025-08-12 | 2025-10-11 | 18500 | Procurement Specialist, Project Manager
1.3.2.1 | Material Procurement Coordination | 2025-08-12 | 2025-08-12 | 1000 | Procurement Specialist, Project Manager
1.3.2.2 | Procurement Approach | 2025-08-13 | 2025-08-13 | 1000 | Procurement Specialist, Project Manager
1.3.2.3 | Procurement Requirements | 2025-08-14 | 2025-08-14 | 1000 | Business Analyst, Project Manager
1.3.2.4 | Supplier Evaluation And Selection Criteria | 2025-08-15 | 2025-09-28 | 7500 | General Project Team
1.3.2.4.1 | Vendor 1 | 2025-08-15 | 2025-08-29 | 2500 | General Project Team
1.3.2.4.2 | Vendor 1 Cost Compeitiveness | 2025-08-15 | 2025-08-17 | 500 | Financial Analyst, Project Manager
1.3.2.4.3 | Vendor 1 Quality Compliance | 2025-08-18 | 2025-08-20 | 500 | Quality Assurance Engineer, Project Manager
1.3.2.4.4 | Vendor 1 Delivery Timeliness | 2025-08-21 | 2025-08-23 | 500 | General Project Team
1.3.2.4.5 | Vendor 1 Vendor Reputation | 2025-08-24 | 2025-08-26 | 500 | General Project Team
1.3.2.4.6 | Vendor 1 After Sales Support | 2025-08-27 | 2025-08-29 | 500 | General Project Team
1.3.2.4.7 | Vendor 2 | 2025-08-30 | 2025-09-13 | 2500 | General Project Team
1.3.2.4.8 | Vendor 2 Cost Compeitiveness | 2025-08-30 | 2025-09-01 | 500 | Financial Analyst, Project Manager
1.3.2.4.9 | Vendor 2 Quality Compliance | 2025-09-02 | 2025-09-04 | 500 | Quality Assurance Engineer, Project Manager
1.3.2.4.10 | Vendor 2 Delivery Timeliness | 2025-09-05 | 2025-09-07 | 500 | General Project Team
1.3.2.4.11 | Vendor 2 Vendor Reputation | 2025-09-08 | 2025-09-10 | 500 | General Project Team
1.3.2.4.12 | Vendor 2 After Sales Support | 2025-09-11 | 2025-09-13 | 500 | General Project Team
1.3.2.4.13 | Vendor 3 | 2025-09-14 | 2025-09-28 | 2500 | General Project Team
1.3.2.4.14 | Vendor 3 Cost Compeitiveness | 2025-09-14 | 2025-09-16 | 500 | Financial Analyst, Project Manager
1.3.2.4.15 | Vendor 3 Quality Compliance | 2025-09-17 | 2025-09-19 | 500 | Quality Assurance Engineer, Project Manager
1.3.2.4.16 | Vendor 3 Delivery Timeliness | 2025-09-20 | 2025-09-22 | 500 | General Project Team
1.3.2.4.17 | Vendor 3 Vendor Reputation | 2025-09-23 | 2025-09-25 | 500 | General Project Team
1.3.2.4.18 | Vendor 3 After Sales Support | 2025-09-26 | 2025-09-28 | 500 | General Project Team
1.3.2.5 | Procurement Schedule | 2025-09-29 | 2025-09-29 | 1000 | Project Scheduler, Project Manager
1.3.2.6 | Request for Proposal For All 3 Vendors | 2025-09-29 | 2025-09-30 | 1000 | General Project Team
1.3.2.7 | Purchase Order For All 3 Vendors | 2025-10-01 | 2025-10-02 | 1000 | General Project Team
1.3.2.8 | Contract Agreement For All 3 Vendors | 2025-10-03 | 2025-10-04 | 1000 | General Project Team
1.3.2.9 | Procurement Risk Management | 2025-10-05 | 2025-10-06 | 1000 | Risk Manager, Project Manager
1.3.2.10 | Present Vendor Options to Project Sponsor | 2025-10-07 | 2025-10-08 | 1000 | General Project Team
1.3.2.11 | Receive Project sponsor Apporval on Vendor 2 | 2025-10-09 | 2025-10-10 | 1000 | General Project Team
1.3.2.12 | Project Parts Procurement Kick-off | 2025-10-11 | 2025-10-11 | 1000 | Procurement Specialist, Project Manager
1.3.3 | Quality Report of Procured Parts | 2025-10-12 | 2025-10-20 | 13000 | Quality Assurance Engineer, Project Manager
1.3.3.1 | Creation Of Quality Report of Procured Parts | 2025-10-12 | 2025-10-17 | 8000 | Quality Assurance Engineer, Project Manager
1.3.3.1.1 | Quality Metrics and KPIS | 2025-10-12 | 2025-10-12 | 1000 | Quality Assurance Engineer, Project Manager
1.3.3.1.2 | Quality Assurance Activities | 2025-10-12 | 2025-10-13 | 1000 | Quality Assurance Engineer, Project Manager
1.3.3.1.3 | Quality Control Activities | 2025-10-13 | 2025-10-13 | 1000 | Quality Assurance Engineer, Project Manager
1.3.3.1.4 | Non-Conformance Reports | 2025-10-14 | 2025-10-14 | 1000 | General Project Team
1.3.3.1.5 | Risk Assesmnet on Part Quality | 2025-10-14 | 2025-10-15 | 1000 | Risk Manager, Project Manager
1.3.3.1.6 | Corrective and Preventive Actions | 2025-10-15 | 2025-10-15 | 1000 | General Project Team
1.3.3.1.7 | Continuous Improvement Process | 2025-10-16 | 2025-10-16 | 1000 | General Project Team
1.3.3.1.8 | Recommendations | 2025-10-16 | 2025-10-17 | 1000 | General Project Team
1.3.3.2 | Development of Quality Report of Procured Parts | 2025-10-18 | 2025-10-19 | 5000 | Quality Assurance Engineer, Project Manager
1.3.3.3 | Approval of Quality Report of Procured Parts | 2025-10-20 | 2025-10-20 | 0 | Quality Assurance Engineer, Project Manager
1.3.4 | Production Trial Phase Initiation | 2025-10-21 | 2026-03-31 | 178000 | Project Manager, Project Sponsor
1.3.4.1 | Software Production Initiated | 2025-10-21 | 2026-01-09 | 55000 | General Project Team
1.3.4.1.1 | Creation of Software | 2025-10-21 | 2026-01-06 | 12000 | General Project Team
1.3.4.1.1.1 | Progress Report | 2025-10-21 | 2025-11-03 | 12000 | General Project Team
1.3.4.1.1.1.1 | Creation Of Software Development Progress Report | 2025-10-21 | 2025-10-31 | 10000 | General Project Team
1.3.4.1.1.1.1.1 | Milestone Status | 2025-10-22 | 2025-10-22 | 1000 | General Project Team
1.3.4.1.1.1.1.2 | Work Completed In This Period | 2025-10-23 | 2025-10-23 | 1000 | General Project Team
1.3.4.1.1.1.1.3 | Work planned for next period | 2025-10-24 | 2025-10-24 | 1000 | General Project Team
1.3.4.1.1.1.1.4 | Progress Performance Metrics | 2025-10-25 | 2025-10-25 | 1000 | General Project Team
1.3.4.1.1.1.1.5 | Budget Status | 2025-10-26 | 2025-10-26 | 1000 | Financial Analyst, Project Manager
1.3.4.1.1.1.1.6 | Key Risks and Issues | 2025-10-27 | 2025-10-27 | 1000 | Risk Manager, Project Manager
1.3.4.1.1.1.1.7 | Dependencies | 2025-10-28 | 2025-10-28 | 1000 | General Project Team
1.3.4.1.1.1.1.8 | Change Requests | 2025-10-29 | 2025-10-29 | 1000 | General Project Team
1.3.4.1.1.1.1.9 | Upcoming Milestones | 2025-10-30 | 2025-10-30 | 1000 | General Project Team
1.3.4.1.1.1.1.10 | Recommendations and Action Items | 2025-10-31 | 2025-10-31 | 1000 | General Project Team
1.3.4.1.1.2 | Develop Software Development Progress Report | 2025-11-01 | 2025-11-02 | 2000 | General Project Team
1.3.4.1.1.3 | Approval of Software Development Progress Report | 2025-11-03 | 2025-11-03 | 0 | General Project Team
1.3.4.1.2 | Development of Software | 2025-11-04 | 2025-12-03 | 10000 | Software Engineering Team
1.3.4.1.3 | Testing of Software | 2025-12-04 | 2025-12-21 | 8000 | Software Engineering Team, Software Testing Team
1.3.4.1.4 | Quality Check Of Software | 2025-12-22 | 2025-12-28 | 5000 | Quality Assurance Engineer, Project Manager
1.3.4.1.5 | Quality Report of Software | 2025-12-29 | 2026-01-06 | 10000 | Quality Assurance Engineer, Project Manager
1.3.4.1.5.1 | Creation of Software Quality Report | 2025-12-29 | 2026-01-03 | 8000 | Quality Assurance Engineer, Project Manager
1.3.4.1.5.1.1 | Quality Metrics and KPIS | 2025-12-29 | 2025-12-29 | 1000 | Quality Assurance Engineer, Project Manager
1.3.4.1.5.1.2 | Quality Assurance Activities | 2025-12-29 | 2025-12-30 | 1000 | Quality Assurance Engineer, Project Manager
1.3.4.1.5.1.3 | Quality Control Activities | 2025-12-30 | 2025-12-30 | 1000 | Quality Assurance Engineer, Project Manager
1.3.4.1.5.1.4 | Non-Conformance Reports | 2025-12-31 | 2025-12-31 | 1000 | General Project Team
1.3.4.1.5.1.5 | Risk Assesmnet on Part Quality | 2025-12-31 | 2026-01-01 | 1000 | Risk Manager, Project Manager
1.3.4.1.5.1.6 | Corrective and Preventive Actions | 2026-01-01 | 2026-01-01 | 1000 | General Project Team
1.3.4.1.5.1.7 | Continuous Improvement Process | 2026-01-02 | 2026-01-02 | 1000 | General Project Team
1.3.4.1.5.1.8 | Recommendations | 2026-01-02 | 2026-01-03 | 1000 | General Project Team
1.3.4.1.5.2 | Develop Software Quality Report | 2026-01-04 | 2026-01-05 | 2000 | Quality Assurance Engineer, Project Manager
1.3.4.1.5.3 | Approval of Software Quality Report | 2026-01-06 | 2026-01-06 | 0 | Quality Assurance Engineer, Project Manager
1.3.4.1.6 | Development Of Software Complete | 2026-01-07 | 2026-01-08 | 5000 | General Project Team
1.3.4.1.7 | Approval of Software | 2026-01-09 | 2026-01-09 | 0 | General Project Team
1.3.4.2 | Hardware Production Initiated | 2025-10-21 | 2026-01-09 | 63000 | General Project Team
1.3.4.2.1 | Creation of Hardware Component | 2025-10-21 | 2026-01-06 | 12000 | General Project Team
1.3.4.2.1.1 | Progress Report | 2025-10-21 | 2025-11-03 | 12000 | General Project Team
1.3.4.2.1.1.1 | Creation Of Hardware Development Progress Report | 2025-10-21 | 2025-10-31 | 10000 | General Project Team
1.3.4.2.1.1.1.1 | Milestone Status | 2025-10-21 | 2025-10-22 | 1000 | General Project Team
1.3.4.2.1.1.1.2 | Work Completed In This Period | 2025-10-23 | 2025-10-23 | 1000 | General Project Team
1.3.4.2.1.1.1.3 | Work planned for next period | 2025-10-24 | 2025-10-24 | 1000 | General Project Team
1.3.4.2.1.1.1.4 | Progress Performance Metrics | 2025-10-25 | 2025-10-25 | 1000 | General Project Team
1.3.4.2.1.1.1.5 | Budget Status | 2025-10-26 | 2025-10-26 | 1000 | Financial Analyst, Project Manager
1.3.4.2.1.1.1.6 | Key Risks and Issues | 2025-10-27 | 2025-10-27 | 1000 | Risk Manager, Project Manager
1.3.4.2.1.1.1.7 | Dependencies | 2025-10-28 | 2025-10-28 | 1000 | General Project Team
1.3.4.2.1.1.1.8 | Change Requests | 2025-10-29 | 2025-10-29 | 1000 | General Project Team
1.3.4.2.1.1.1.9 | Upcoming Milestones | 2025-10-30 | 2025-10-30 | 1000 | General Project Team
1.3.4.2.1.1.1.10 | Recommendations and Action Items | 2025-10-31 | 2025-10-31 | 1000 | General Project Team
1.3.4.2.1.1.2 | Develop Hardware Development Progress Report | 2025-11-01 | 2025-11-02 | 2000 | General Project Team
1.3.4.2.1.1.3 | Approval of Hardware Development Progress Report | 2025-11-03 | 2025-11-03 | 0 | General Project Team
1.3.4.2.2 | Development of Hardware | 2025-11-04 | 2025-12-03 | 15000 | Hardware Engineering Team
1.3.4.2.3 | Testing of Hardware | 2025-12-04 | 2025-12-21 | 10000 | Hardware Engineering Team, Hardware Testing Team
1.3.4.2.4 | Quality Check Of Hardware | 2025-12-22 | 2025-12-28 | 8000 | Quality Assurance Engineer, Project Manager
1.3.4.2.5 | Quality Report of Hadware | 2025-12-29 | 2026-01-06 | 13000 | Quality Assurance Engineer, Project Manager
1.3.4.2.5.1 | Creation of Hardware Quality Report | 2025-12-29 | 2026-01-03 | 8000 | Quality Assurance Engineer, Project Manager
1.3.4.2.5.1.1 | Quality Metrics and KPIS | 2025-12-29 | 2025-12-29 | 1000 | Quality Assurance Engineer, Project Manager
1.3.4.2.5.1.2 | Quality Assurance Activities | 2025-12-29 | 2025-12-30 | 1000 | Quality Assurance Engineer, Project Manager
1.3.4.2.5.1.3 | Quality Control Activities | 2025-12-30 | 2025-12-30 | 1000 | Quality Assurance Engineer, Project Manager
1.3.4.2.5.1.4 | Non-Conformance Reports | 2025-12-31 | 2025-12-31 | 1000 | General Project Team
1.3.4.2.5.1.5 | Risk Assesmnet on Part Quality | 2025-12-31 | 2026-01-01 | 1000 | Risk Manager, Project Manager
1.3.4.2.5.1.6 | Corrective and Preventive Actions | 2026-01-01 | 2026-01-01 | 1000 | General Project Team
1.3.4.2.5.1.7 | Continuous Improvement Process | 2026-01-02 | 2026-01-02 | 1000 | General Project Team
1.3.4.2.5.1.8 | Recommendations | 2026-01-02 | 2026-01-03 | 1000 | General Project Team
1.3.4.2.5.2 | Develop Hadware Quality Report | 2026-01-04 | 2026-01-05 | 5000 | Quality Assurance Engineer, Project Manager
1.3.4.2.5.3 | Approval of Hardware Quality Report | 2026-01-06 | 2026-01-06 | 0 | Quality Assurance Engineer, Project Manager
1.3.4.2.6 | Development Of Hardware Complete | 2026-01-07 | 2026-01-08 | 5000 | General Project Team
1.3.4.2.7 | Approval of Hardware | 2026-01-09 | 2026-01-09 | 0 | General Project Team
1.3.4.3 | Software and Hardware Integration Initiated | 2026-01-10 | 2026-03-31 | 60000 | General Project Team
1.3.4.3.1 | Integration of Software and Hardware Module | 2026-01-10 | 2026-03-28 | 12000 | General Project Team
1.3.4.3.1.1 | Progress Report | 2026-01-10 | 2026-01-23 | 10000 | General Project Team
1.3.4.3.1.1.1 | Creation Of Integrated SW/HW Module Progress Report | 2026-01-10 | 2026-01-20 | 10000 | General Project Team
1.3.4.3.1.1.1.1 | Milestone Status | 2026-01-10 | 2026-01-11 | 1000 | General Project Team
1.3.4.3.1.1.1.2 | Work Completed In This Period | 2026-01-12 | 2026-01-12 | 1000 | General Project Team
1.3.4.3.1.1.1.3 | Work planned for next period | 2026-01-13 | 2026-01-13 | 1000 | General Project Team
1.3.4.3.1.1.1.4 | Progress Performance Metrics | 2026-01-14 | 2026-01-14 | 1000 | General Project Team
1.3.4.3.1.1.1.5 | Budget Status | 2026-01-15 | 2026-01-15 | 1000 | Financial Analyst, Project Manager
1.3.4.3.1.1.1.6 | Key Risks and Issues | 2026-01-16 | 2026-01-16 | 1000 | Risk Manager, Project Manager
1.3.4.3.1.1.1.7 | Dependencies | 2026-01-17 | 2026-01-17 | 1000 | General Project Team
1.3.4.3.1.1.1.8 | Change Requests | 2026-01-18 | 2026-01-18 | 1000 | General Project Team
1.3.4.3.1.1.1.9 | Upcoming Milestones | 2026-01-19 | 2026-01-19 | 1000 | General Project Team
1.3.4.3.1.1.1.10 | Recommendations and Action Items | 2026-01-20 | 2026-01-20 | 1000 | General Project Team
1.3.4.3.1.1.2 | Develop Integrated SW/HW Module Progress Report | 2026-01-21 | 2026-01-22 | 2000 | General Project Team
1.3.4.3.1.1.3 | Approval of Integrated SW/HW Module Progress Report | 2026-01-23 | 2026-01-23 | 0 | General Project Team
1.3.4.3.2 | Development of Integrated SW/HW Module | 2026-01-24 | 2026-02-23 | 15000 | General Project Team
1.3.4.3.3 | Testing of Integrated SW/HW Module | 2026-02-24 | 2026-03-10 | 10000 | General Project Team
1.3.4.3.4 | Quality Check Of Integrated SW/HW Module | 2026-03-11 | 2026-03-17 | 8000 | Quality Assurance Engineer, Project Manager
1.3.4.3.5 | Quality Report of Integrated SW/HW Module | 2026-03-18 | 2026-03-28 | 10000 | Quality Assurance Engineer, Project Manager
1.3.4.3.5.1 | Creation of Integrated SW/HW Module Quality Report | 2026-03-18 | 2026-03-25 | 8000 | Quality Assurance Engineer, Project Manager
1.3.4.3.5.1.1 | Quality Metrics and KPIS | 2026-03-18 | 2026-03-18 | 1000 | Quality Assurance Engineer, Project Manager
1.3.4.3.5.1.2 | Quality Assurance Activities | 2026-03-19 | 2026-03-19 | 1000 | Quality Assurance Engineer, Project Manager
1.3.4.3.5.1.3 | Quality Control Activities | 2026-03-20 | 2026-03-20 | 1000 | Quality Assurance Engineer, Project Manager
1.3.4.3.5.1.4 | Non-Conformance Reports | 2026-03-21 | 2026-03-21 | 1000 | General Project Team
1.3.4.3.5.1.5 | Risk Assesmnet on Part Quality | 2026-03-22 | 2026-03-22 | 1000 | Risk Manager, Project Manager
1.3.4.3.5.1.6 | Corrective and Preventive Actions | 2026-03-23 | 2026-03-23 | 1000 | General Project Team
1.3.4.3.5.1.7 | Continuous Improvement Process | 2026-03-24 | 2026-03-24 | 1000 | General Project Team
1.3.4.3.5.1.8 | Recommendations | 2026-03-25 | 2026-03-25 | 1000 | General Project Team
1.3.4.3.5.2 | Develop Integrated SW/HW Module Quality Report | 2026-03-26 | 2026-03-27 | 2000 | Quality Assurance Engineer, Project Manager
1.3.4.3.5.3 | Approval of Integrated SW/HW Module Quality Report | 2026-03-28 | 2026-03-28 | 0 | Quality Assurance Engineer, Project Manager
1.3.4.3.6 | Development Of Integrated SW/HW Module Complete | 2026-03-29 | 2026-03-30 | 5000 | General Project Team
1.3.4.3.7 | Approval of Integrated SW/HW Module | 2026-03-31 | 2026-03-31 | 0 | General Project Team
1.3.5 | Issue Logs | 2026-04-01 | 2026-04-09 | 11000 | General Project Team
1.3.5.1 | Creation of Issue Logs | 2026-04-01 | 2026-04-06 | 6000 | General Project Team
1.3.5.1.1 | Issue Log Template | 2026-04-01 | 2026-04-01 | 1000 | General Project Team
1.3.5.1.2 | Issue Prioritization Criteria | 2026-04-02 | 2026-04-02 | 1000 | General Project Team
1.3.5.1.3 | Issue Status Definitions | 2026-04-03 | 2026-04-03 | 1000 | General Project Team
1.3.5.1.4 | Issue Management Process | 2026-04-04 | 2026-04-04 | 1000 | General Project Team
1.3.5.1.5 | Issue Escalation Process | 2026-04-05 | 2026-04-05 | 1000 | General Project Team
1.3.5.1.6 | Issue Review Frequency | 2026-04-06 | 2026-04-06 | 1000 | General Project Team
1.3.5.2 | Develop Issue Log | 2026-04-07 | 2026-04-08 | 5000 | General Project Team
1.3.5.3 | Approval of Issue Log | 2026-04-09 | 2026-04-09 | 0 | General Project Team
1.3.6 | Change Request Form | 2026-04-10 | 2026-04-20 | 13000 | General Project Team
1.3.6.1 | Create Change Request Form | 2026-04-10 | 2026-04-17 | 8000 | General Project Team
1.3.6.1.1 | Change Request Information | 2026-04-10 | 2026-04-10 | 1000 | General Project Team
1.3.6.1.2 | Change Description | 2026-04-11 | 2026-04-11 | 1000 | General Project Team
1.3.6.1.3 | Impact Analysis | 2026-04-12 | 2026-04-12 | 1000 | General Project Team
1.3.6.1.4 | Proposed Solution/Action Plan | 2026-04-13 | 2026-04-13 | 1000 | General Project Team
1.3.6.1.5 | Estimated Cost And Time Impact | 2026-04-14 | 2026-04-14 | 1000 | Financial Analyst, Project Manager
1.3.6.1.6 | Implementation Details | 2026-04-15 | 2026-04-15 | 1000 | General Project Team
1.3.6.1.7 | Comments/Additional Notes | 2026-04-16 | 2026-04-16 | 1000 | General Project Team
1.3.6.1.8 | Final Status | 2026-04-17 | 2026-04-17 | 1000 | General Project Team
1.3.6.2 | Develop Change Request Form | 2026-04-18 | 2026-04-19 | 5000 | General Project Team
1.3.6.3 | Approval of Change Request Form | 2026-04-20 | 2026-04-20 | 0 | General Project Team
1.3.7 | Performace Report | 2026-04-21 | 2026-05-03 | 15000 | General Project Team
1.3.7.1 | Create Performance Reports | 2026-04-21 | 2026-04-30 | 10000 | General Project Team
1.3.7.1.1 | Project Objectives And Performance Metrics | 2026-04-21 | 2026-04-21 | 1000 | General Project Team
1.3.7.1.2 | Key Milestones and Deliverable Status | 2026-04-22 | 2026-04-22 | 1000 | General Project Team
1.3.7.1.3 | Performance Indicators | 2026-04-23 | 2026-04-23 | 1000 | General Project Team
1.3.7.1.4 | Risk And Issue Management | 2026-04-24 | 2026-04-24 | 1000 | Risk Manager, Project Manager
1.3.7.1.5 | Budget Performance | 2026-04-25 | 2026-04-25 | 1000 | Financial Analyst, Project Manager
1.3.7.1.6 | Work Completed This Period | 2026-04-26 | 2026-04-26 | 1000 | General Project Team
1.3.7.1.7 | Work planned for next period | 2026-04-27 | 2026-04-27 | 1000 | General Project Team
1.3.7.1.8 | Creative and Preventive Actions | 2026-04-28 | 2026-04-28 | 1000 | General Project Team
1.3.7.1.9 | Recommendations | 2026-04-29 | 2026-04-29 | 1000 | General Project Team
1.3.7.1.10 | Next Steps | 2026-04-30 | 2026-04-30 | 1000 | General Project Team
1.3.7.2 | Develop Performance Reports | 2026-05-01 | 2026-05-02 | 5000 | General Project Team
1.3.7.3 | Approval of Performance Reports | 2026-05-03 | 2026-05-03 | 0 | General Project Team
| Project Execution Phase Completed | 2026-05-03 | 2026-05-03 | 0 | General Project Team
1.4 | Project Monitoring and Controlling | 2026-05-04 | 2026-06-23 | 63000 | General Project Team
1.4.1 | Project Status Reports | 2026-05-04 | 2026-05-14 | 13000 | General Project Team
1.4.1.1 | Create Project Status Reports | 2026-05-04 | 2026-05-11 | 8000 | General Project Team
1.4.1.1.1 | Project Progress | 2026-05-04 | 2026-05-04 | 1000 | General Project Team
1.4.1.1.2 | Milestones And Deliverables | 2026-05-05 | 2026-05-05 | 1000 | General Project Team
1.4.1.1.3 | Financial Performance | 2026-05-06 | 2026-05-06 | 1000 | General Project Team
1.4.1.1.4 | Risks and Issues | 2026-05-07 | 2026-05-07 | 1000 | Risk Manager, Project Manager
1.4.1.1.5 | Key Performance Indicators (KPIs) | 2026-05-08 | 2026-05-08 | 1000 | General Project Team
1.4.1.1.6 | Change Requests | 2026-05-09 | 2026-05-09 | 1000 | General Project Team
1.4.1.1.7 | Recommendations | 2026-05-10 | 2026-05-10 | 1000 | General Project Team
1.4.1.1.8 | Next Steps | 2026-05-11 | 2026-05-11 | 1000 | General Project Team
1.4.1.2 | Develop Project Status Reports | 2026-05-12 | 2026-05-13 | 5000 | General Project Team
1.4.1.3 | Approval of Project Status Reports | 2026-05-14 | 2026-05-14 | 0 | General Project Team
1.4.2 | Risk Register (Updated) | 2026-05-15 | 2026-05-23 | 11000 | Risk Manager, Project Manager
1.4.2.1 | Create Updated Risk Register | 2026-05-15 | 2026-05-20 | 6000 | Risk Manager, Project Manager
1.4.2.1.1 | Risk Register | 2026-05-15 | 2026-05-15 | 1000 | Risk Manager, Project Manager
1.4.2.1.2 | Risk Prioritization Matrix | 2026-05-16 | 2026-05-16 | 1000 | Risk Manager, Project Manager
1.4.2.1.3 | Key Risks Details | 2026-05-17 | 2026-05-17 | 1000 | Risk Manager, Project Manager
1.4.2.1.4 | Risk Monitoring and Review | 2026-05-18 | 2026-05-18 | 1000 | Risk Manager, Project Manager
1.4.2.1.5 | Risk Updates and Notes | 2026-05-19 | 2026-05-19 | 1000 | Risk Manager, Project Manager
1.4.2.1.6 | Risk Escalation Plan | 2026-05-20 | 2026-05-20 | 1000 | Risk Manager, Project Manager
1.4.2.2 | Develop Updated Risk Register | 2026-05-21 | 2026-05-22 | 5000 | Risk Manager, Project Manager
1.4.2.3 | Approval of Updated Risk Register | 2026-05-23 | 2026-05-23 | 0 | Risk Manager, Project Manager
1.4.3 | Issue Log (Updated) | 2026-05-24 | 2026-05-31 | 10000 | General Project Team
1.4.3.1 | Create Updated Issue Log | 2026-05-24 | 2026-05-28 | 5000 | General Project Team
1.4.3.1.1 | Issue Log | 2026-05-24 | 2026-05-24 | 1000 | General Project Team
1.4.3.1.2 | Issue Prioritization Matrix | 2026-05-25 | 2026-05-25 | 1000 | General Project Team
1.4.3.1.3 | Key Issue Details | 2026-05-26 | 2026-05-26 | 1000 | General Project Team
1.4.3.1.4 | Issue Monitoring | 2026-05-27 | 2026-05-27 | 1000 | General Project Team
1.4.3.1.5 | New Issues Identified | 2026-05-28 | 2026-05-28 | 1000 | General Project Team
1.4.3.2 | Develop Updated Issue Log | 2026-05-29 | 2026-05-30 | 5000 | General Project Team
1.4.3.3 | Approval of Updated Issue log | 2026-05-31 | 2026-05-31 | 0 | General Project Team
1.4.4 | Change Log | 2026-06-01 | 2026-06-08 | 10000 | General Project Team
1.4.4.1 | Create Change Log | 2026-06-01 | 2026-06-05 | 5000 | General Project Team
1.4.4.1.1 | Change Log Table | 2026-06-01 | 2026-06-01 | 1000 | General Project Team
1.4.4.1.2 | Change Prioritization | 2026-06-02 | 2026-06-02 | 1000 | General Project Team
1.4.4.1.3 | Change Details | 2026-06-03 | 2026-06-03 | 1000 | General Project Team
1.4.4.1.4 | Change Request Review Process | 2026-06-04 | 2026-06-04 | 1000 | General Project Team
1.4.4.1.5 | Summary of Approved Changes | 2026-06-05 | 2026-06-05 | 1000 | General Project Team
1.4.4.2 | Develop Change Log | 2026-06-06 | 2026-06-07 | 5000 | General Project Team
1.4.4.3 | Approval of Change Log | 2026-06-08 | 2026-06-08 | 0 | General Project Team
1.4.5 | Variance Analysis Report | 2026-06-09 | 2026-06-15 | 9000 | General Project Team
1.4.5.1 | Create Variance Analysis Report | 2026-06-09 | 2026-06-12 | 4000 | General Project Team
1.4.5.1.1 | Variance Summary | 2026-06-09 | 2026-06-09 | 1000 | General Project Team
1.4.5.1.2 | Detailed Variance Analysis | 2026-06-10 | 2026-06-10 | 1000 | General Project Team
1.4.5.1.3 | Performance Metrics | 2026-06-11 | 2026-06-11 | 1000 | General Project Team
1.4.5.1.4 | Recommendations | 2026-06-12 | 2026-06-12 | 1000 | General Project Team
1.4.5.2 | Develop Variance Analysis Report | 2026-06-13 | 2026-06-14 | 5000 | General Project Team
1.4.5.3 | Approval of Variance Analysis Report | 2026-06-15 | 2026-06-15 | 0 | General Project Team
1.4.6 | Lessons Learned Register | 2026-06-16 | 2026-06-23 | 10000 | General Project Team
1.4.6.1 | Create Lessons Learned Register | 2026-06-16 | 2026-06-20 | 5000 | General Project Team
1.4.6.1.1 | Key Lessons Learned | 2026-06-16 | 2026-06-16 | 1000 | General Project Team
1.4.6.1.2 | Metrics Analysis | 2026-06-17 | 2026-06-17 | 1000 | General Project Team
1.4.6.1.3 | Stakeholder Feedback | 2026-06-18 | 2026-06-18 | 1000 | Stakeholder Engagement Manager, Business Analyst
1.4.6.1.4 | Key Takeaways | 2026-06-19 | 2026-06-19 | 1000 | General Project Team
1.4.6.1.5 | Recommendations For Future Projects | 2026-06-20 | 2026-06-20 | 1000 | General Project Team
1.4.6.2 | Develop Lessons Learned Register | 2026-06-21 | 2026-06-22 | 5000 | General Project Team
1.4.6.3 | Approval of Lessons Learned Register | 2026-06-23 | 2026-06-23 | 0 | General Project Team
| Project Monitoring and Controlling Phase Completed | 2026-06-23 | 2026-06-23 | 0 | General Project Team
1.5 | Project Closing | 2026-06-24 | 2026-09-06 | 91000 | General Project Team
1.5.1 | Project Closure Report | 2026-06-24 | 2026-07-04 | 13000 | General Project Team
1.5.1.1 | Create Project Closure Report | 2026-06-24 | 2026-07-01 | 8000 | General Project Team
1.5.1.1.1 | Project Deliverables | 2026-06-24 | 2026-06-24 | 1000 | General Project Team
1.5.1.1.2 | Performance Against Objectives | 2026-06-25 | 2026-06-25 | 1000 | General Project Team
1.5.1.1.3 | Lessons Learned | 2026-06-26 | 2026-06-26 | 1000 | General Project Team
1.5.1.1.4 | Key Successes | 2026-06-27 | 2026-06-27 | 1000 | General Project Team
1.5.1.1.5 | Issues Encountered | 2026-06-28 | 2026-06-28 | 1000 | General Project Team
1.5.1.1.6 | Stakeholder Feedback | 2026-06-29 | 2026-06-29 | 1000 | Stakeholder Engagement Manager, Business Analyst
1.5.1.1.7 | Final Financial Summary | 2026-06-30 | 2026-06-30 | 1000 | General Project Team
1.5.1.1.8 | Recommendations | 2026-07-01 | 2026-07-01 | 1000 | General Project Team
1.5.1.2 | Develop Project Closure Report | 2026-07-02 | 2026-07-03 | 5000 | General Project Team
1.5.1.3 | Approval of Project Closure Report | 2026-07-04 | 2026-07-04 | 0 | General Project Team
1.5.2 | Final Deliverables Report | 2026-07-05 | 2026-07-13 | 11000 | General Project Team
1.5.2.1 | Create Final Deliverables Report | 2026-07-05 | 2026-07-10 | 6000 | General Project Team
1.5.2.1.1 | Final Deliverables Summary | 2026-07-05 | 2026-07-05 | 1000 | General Project Team
1.5.2.1.2 | Detailed Deliverables Descriptions | 2026-07-06 | 2026-07-06 | 1000 | General Project Team
1.5.2.1.3 | Deliverable Approval | 2026-07-07 | 2026-07-07 | 1000 | General Project Team
1.5.2.1.4 | Documentation Associated With Deliverables | 2026-07-08 | 2026-07-08 | 1000 | General Project Team
1.5.2.1.5 | Handover To Operations | 2026-07-09 | 2026-07-09 | 1000 | General Project Team
1.5.2.1.6 | Recommendations For Future Projects | 2026-07-10 | 2026-07-10 | 1000 | General Project Team
1.5.2.2 | Develop Final Deliverables Report | 2026-07-11 | 2026-07-12 | 5000 | General Project Team
1.5.2.3 | Approval of Final Deliverables Report | 2026-07-13 | 2026-07-13 | 0 | General Project Team
1.5.3 | Final Budget Report | 2026-07-14 | 2026-07-23 | 12000 | Financial Analyst, Project Manager
1.5.3.1 | Create Final Budget Report | 2026-07-14 | 2026-07-20 | 7000 | Financial Analyst, Project Manager
1.5.3.1.1 | Budget Overview | 2026-07-14 | 2026-07-14 | 1000 | Financial Analyst, Project Manager
1.5.3.1.2 | Budget Summary | 2026-07-15 | 2026-07-15 | 1000 | Financial Analyst, Project Manager
1.5.3.1.3 | Cost Performance Analysis | 2026-07-16 | 2026-07-16 | 1000 | Financial Analyst, Project Manager
1.5.3.1.4 | Key Variances | 2026-07-17 | 2026-07-17 | 1000 | General Project Team
1.5.3.1.5 | Major Cost Drivers | 2026-07-18 | 2026-07-18 | 1000 | Financial Analyst, Project Manager
1.5.3.1.6 | Recommendations For Future Projects | 2026-07-19 | 2026-07-19 | 1000 | General Project Team
1.5.3.1.7 | Lessons Learned | 2026-07-20 | 2026-07-20 | 1000 | General Project Team
1.5.3.2 | Develop Final Budget Report | 2026-07-21 | 2026-07-22 | 5000 | Financial Analyst, Project Manager
1.5.3.3 | Approval of Final Budget Report | 2026-07-23 | 2026-07-23 | 0 | Financial Analyst, Project Manager
1.5.4 | Contract Closure Documents | 2026-07-24 | 2026-08-02 | 12000 | General Project Team
1.5.4.1 | Create Contract Closure Documents | 2026-07-24 | 2026-07-30 | 7000 | General Project Team
1.5.4.1.1 | Contract Overview | 2026-07-24 | 2026-07-24 | 1000 | General Project Team
1.5.4.1.2 | Deliverables Summary | 2026-07-25 | 2026-07-25 | 1000 | General Project Team
1.5.4.1.3 | Contract Closure Checklist | 2026-07-26 | 2026-07-26 | 1000 | General Project Team
1.5.4.1.4 | Financial Summary | 2026-07-27 | 2026-07-27 | 1000 | General Project Team
1.5.4.1.5 | Lessons Learned | 2026-07-28 | 2026-07-28 | 1000 | General Project Team
1.5.4.1.6 | Vendor Performance Reviews | 2026-07-29 | 2026-07-29 | 1000 | General Project Team
1.5.4.1.7 | Outstanding Issues | 2026-07-30 | 2026-07-30 | 1000 | General Project Team
1.5.4.2 | Develop Contract Closure Documents | 2026-07-31 | 2026-08-01 | 5000 | General Project Team
1.5.4.3 | Approval Of Contract Closure Documents | 2026-08-02 | 2026-08-02 | 0 | General Project Team
1.5.5 | Handover Documents Report | 2026-08-03 | 2026-08-12 | 12000 | General Project Team
1.5.5.1 | Create Handover Documents Report | 2026-08-03 | 2026-08-09 | 7000 | General Project Team
1.5.5.1.1 | Final Deliverables | 2026-08-03 | 2026-08-03 | 1000 | General Project Team
1.5.5.1.2 | Key Contacts | 2026-08-04 | 2026-08-04 | 1000 | General Project Team
1.5.5.1.3 | Handover Details | 2026-08-05 | 2026-08-05 | 1000 | General Project Team
1.5.5.1.4 | Documentation Provided | 2026-08-06 | 2026-08-06 | 1000 | General Project Team
1.5.5.1.5 | Outstanding Issues And Recommendations | 2026-08-07 | 2026-08-07 | 1000 | General Project Team
1.5.5.1.6 | Future Maintenance And Support | 2026-08-08 | 2026-08-08 | 1000 | General Project Team
1.5.5.1.7 | Lessons Learned | 2026-08-09 | 2026-08-09 | 1000 | General Project Team
1.5.5.2 | Develop Handover Documents Report | 2026-08-10 | 2026-08-11 | 5000 | General Project Team
1.5.5.3 | Approval Of Handover Documents Report | 2026-08-12 | 2026-08-12 | 0 | General Project Team
1.5.6 | Client Acceptance Form | 2026-08-13 | 2026-08-20 | 10000 | General Project Team
1.5.6.1 | Create Client Acceptance Form | 2026-08-13 | 2026-08-17 | 5000 | General Project Team
1.5.6.1.1 | Accepted Deliverables | 2026-08-13 | 2026-08-13 | 1000 | General Project Team
1.5.6.1.2 | Client Feedback | 2026-08-14 | 2026-08-14 | 1000 | General Project Team
1.5.6.1.3 | Outstanding Issues | 2026-08-15 | 2026-08-15 | 1000 | General Project Team
1.5.6.1.4 | Acknowledgement And Acceptance | 2026-08-16 | 2026-08-16 | 1000 | General Project Team
1.5.6.1.5 | Attachments | 2026-08-17 | 2026-08-17 | 1000 | General Project Team
1.5.6.2 | Develop Client Acceptance Form | 2026-08-18 | 2026-08-19 | 5000 | General Project Team
1.5.6.3 | Approval of Client Acceptance Form | 2026-08-20 | 2026-08-20 | 0 | General Project Team
1.5.7 | Post-Implementation Review | 2026-08-21 | 2026-08-30 | 12000 | General Project Team
1.5.7.1 | Create Post-Implementation Review | 2026-08-21 | 2026-08-27 | 7000 | General Project Team
1.5.7.1.1 | Project Performance Overview | 2026-08-21 | 2026-08-21 | 1000 | General Project Team
1.5.7.1.2 | Key Successes | 2026-08-22 | 2026-08-22 | 1000 | General Project Team
1.5.7.1.3 | Challenges And Lessons Learned | 2026-08-23 | 2026-08-23 | 1000 | General Project Team
1.5.7.1.4 | Metrics Analysis | 2026-08-24 | 2026-08-24 | 1000 | General Project Team
1.5.7.1.5 | Stakeholder Feedback | 2026-08-25 | 2026-08-25 | 1000 | Stakeholder Engagement Manager, Business Analyst
1.5.7.1.6 | Recommendations For Future Projects | 2026-08-26 | 2026-08-26 | 1000 | General Project Team
1.5.7.1.7 | Action Items For Continuous Improvement | 2026-08-27 | 2026-08-27 | 1000 | General Project Team
1.5.7.2 | Develop Post-Implementation Review | 2026-08-28 | 2026-08-29 | 5000 | General Project Team
1.5.7.3 | Approval of Post-Implementation Review | 2026-08-30 | 2026-08-30 | 0 | General Project Team
1.5.8 | Archive Documents Report | 2026-08-31 | 2026-09-06 | 9000 | General Project Team
1.5.8.1 | Create Archive Documents Report | 2026-08-31 | 2026-09-03 | 4000 | General Project Team
1.5.8.1.1 | Contents of the Archive | 2026-08-31 | 2026-08-31 | 1000 | General Project Team
1.5.8.1.2 | Archive Location | 2026-09-01 | 2026-09-01 | 1000 | General Project Team
1.5.8.1.3 | Access Permissions | 2026-09-02 | 2026-09-02 | 1000 | General Project Team
1.5.8.1.4 | Maintenance And Retention Policy | 2026-09-03 | 2026-09-03 | 1000 | General Project Team
1.5.8.2 | Develop Archive Documents Report | 2026-09-04 | 2026-09-05 | 5000 | General Project Team
1.5.8.3 | Approval. Of Archive Documents Report | 2026-09-06 | 2026-09-06 | 0 | General Project Team
| Project Closing Phase Completed | 2026-09-06 | 2026-09-06 | 0 | General Project Team

## Sheet2 (hidden)
E-Collar | 58 days | Mon 9/20/21 | Wed 12/8/21 |  |  | 0%
E-collar WBS | 58 days | Mon 9/20/21 | Wed 12/8/21 |  |  | 0%
Project Initiation | 5 days | Mon 9/20/21 | Fri 9/24/21 |  |  | 0%
Creation of Project Charter | 1 day | Mon 9/20/21 | Mon 9/20/21 |  | Project Manager | 0%
Identify Stakeholders | 2 days | Tue 9/21/21 | Wed 9/22/21 | 3 | Project Manager | 0%
Final Draft of Project Charter | 1 day | Thu 9/23/21 | Thu 9/23/21 | 4 | Project Manager | 0%
Initiate Team Meeting | 1 day | Fri 9/24/21 | Fri 9/24/21 | 5 | Assistant Project Manager | 0%
Project Planning | 18 days | Mon 9/27/21 | Wed 10/20/21 |  |  | 0%
Scope Management | 4 days | Mon 9/27/21 | Thu 9/30/21 |  |  | 0%
Accumulate requirements | 1 day | Mon 9/27/21 | Mon 9/27/21 | 6 | Assistant Project Manager | 0%
Analyse requirements | 1 day | Tue 9/28/21 | Tue 9/28/21 | 9 | Project Manager | 0%
Decide Scope statement and scope baseline | 2 days | Wed 9/29/21 | Thu 9/30/21 | 10 | Project Manager | 0%
Develop WBS | 2 days | Wed 9/29/21 | Thu 9/30/21 | 11SS | Assistant Project Manager | 0%
Schedule Management | 2 days | Fri 10/1/21 | Mon 10/4/21 |  |  | 0%
Determine Sequence of tasks and Estimated Duration of each task | 1 day | Fri 10/1/21 | Fri 10/1/21 | 12 | Assistant Project Manager | 0%
Create Schedule | 1 day | Mon 10/4/21 | Mon 10/4/21 | 14 | Assistant Project Manager | 0%
Cost Management | 2 days | Tue 10/5/21 | Wed 10/6/21 |  |  | 0%
Estimate Cost | 1 day | Tue 10/5/21 | Tue 10/5/21 | 15 | Project Manager | 0%
Develop Budget | 2 days | Tue 10/5/21 | Wed 10/6/21 | 17FF | Project Manager | 0%
Risk Management | 9 days | Thu 10/7/21 | Tue 10/19/21 |  |  | 0%
Recognize Risks | 2 days | Thu 10/7/21 | Fri 10/8/21 | 18 | Project Manager | 0%
Analyse Risk Response (Quantitative and Qualitative) | 2 days | Mon 10/11/21 | Tue 10/12/21 | 20 | Project Manager | 0%
Construct Risk plan | 2 days | Wed 10/13/21 | Thu 10/14/21 | 21 | Assistant Project Manager | 0%
Review Meeting to discuss risk. | 1 day | Fri 10/15/21 | Fri 10/15/21 | 22 | Assistant Project Manager | 0%
Implement Risk Response | 2 days | Mon 10/18/21 | Tue 10/19/21 | 23 | Project Manager | 0%
Stakeholder Management | 1 day | Wed 10/20/21 | Wed 10/20/21 |  |  | 0%
Manage Stakeholders | 1 day | Wed 10/20/21 | Wed 10/20/21 | 24 | Project Manager | 0%
Project Execution | 58 days | Mon 9/20/21 | Wed 12/8/21 |  |  | 0%
Target Audience | 3 days | Tue 10/19/21 | Thu 10/21/21 |  |  | 0%
Identify Target Audience associated with the Project | 2 days | Tue 10/19/21 | Wed 10/20/21 | 26FS-2 days | Media Manager | 0%
Review the data obtained from identification of target audience | 1 day | Thu 10/21/21 | Thu 10/21/21 | 29 | Media Manager | 0%
Review meeting with Pet Technologies | 0 days | Thu 10/21/21 | Thu 10/21/21 | 30 | Project Manager | 0%
Concept for advertising | 6 days | Fri 10/22/21 | Fri 10/29/21 |  |  | 0%
Brainstorm ideas | 1 day | Fri 10/22/21 | Fri 10/22/21 | 31 | Concept Execuitve 1 | 0%
Analysis of concepts | 3 days | Mon 10/25/21 | Wed 10/27/21 | 33 | Concept Executive 2 | 0%
Development of concepts | 2 days | Thu 10/28/21 | Fri 10/29/21 | 34 | Concept Execuitve 1 | 0%
Creative Collateral | 12 days | Mon 11/1/21 | Tue 11/16/21 |  |  | 0%
Determine Media Platforms | 2 days | Mon 11/1/21 | Tue 11/2/21 | 35 | Collateral Executive 1 | 0%
Finalize mix of media | 1 day | Tue 11/9/21 | Tue 11/9/21 | 37FS+4 days | Project Manager | 0%
Create Collaterals | 3 days | Wed 11/10/21 | Fri 11/12/21 | 38 | Collateral Executive 2 | 0%
Gather Feedback from Client | 0 days | Fri 11/12/21 | Fri 11/12/21 | 39 | Assistant Project Manager | 0%
Implement the necessary feedback | 1 day | Mon 11/15/21 | Mon 11/15/21 | 40 | Collateral Executive 1 | 0%
Finalize Collaterals | 1 day | Tue 11/16/21 | Tue 11/16/21 | 41 | Project Manager | 0%
Production of collaterals | 6 days | Wed 11/17/21 | Wed 11/24/21 |  |  | 0%
Outsourcing Production of Selected Media | 6 days | Wed 11/17/21 | Wed 11/24/21 |  |  | 0%
Brief the firm regarding project | 1 day | Wed 11/17/21 | Wed 11/17/21 | 42 | Project Manager | 0%
Provide Feedback | 0 days | Wed 11/17/21 | Wed 11/17/21 | 45 | Assistant Project Manager | 0%
Monitor work | 5 days | Thu 11/18/21 | Wed 11/24/21 | 46 | Assistant Project Manager | 0%
Assign Account Manager | 3 days | Mon 9/20/21 | Wed 9/22/21 |  |  | 0%
Testing | 5 days | Thu 11/25/21 | Wed 12/1/21 |  |  | 0%
Execute the test on the selected target audience | 3 days | Thu 11/25/21 | Mon 11/29/21 | 47 | Collateral Executive 1 | 0%
Study the outcomes | 1 day | Tue 11/30/21 | Tue 11/30/21 | 50 | Collateral Executive 2 | 0%
Prepare Market research report | 1 day | Wed 12/1/21 | Wed 12/1/21 | 51 | Market Researcher | 0%
Launch | 4 days | Thu 12/2/21 | Tue 12/7/21 |  |  | 0%
Launch the campaign | 4 days | Thu 12/2/21 | Tue 12/7/21 | 52 | Project Manager | 0%
Comapre Baseline | 2 days | Tue 12/7/21 | Wed 12/8/21 |  |  | 0%
Compare Testing and Final Findings | 1 day | Tue 12/7/21 | Tue 12/7/21 | 54SS | Assistant Project Manager | 0%
Present the findings to the client | 0 days | Wed 12/8/21 | Wed 12/8/21 | 56 | Assistant Project Manager | 0%
Project Review with the team | 1 day | Wed 12/8/21 | Wed 12/8/21 | 57FF | Project Manager | 0%

## Sheet3 (hidden)
1 | Assign Project Manager | 1 day | Fri 4/22/22 | Fri 4/22/22 |  | Project Manager | 0
2 | Receive Business Case | 1 day | Mon 4/25/22 | Mon 4/25/22 | 1 | Project Manager | 0
3 | Hold Kickoff Meeting | 1 day | Tue 4/26/22 | Tue 4/26/22 | 2 | Project Manager,Assistant Construction Manager,Assistant Project Management,Compset Researcher,Designer 1,Designer 2,Designer 3,Guestroom Construction Manager,Lobby Construction Manager,Local Researcher,Materials Manager,Meeting Space Construction Mana... | 11840
4 | Project Documentation | 43 days | Wed 4/27/22 | Fri 6/24/22 | 3 |  | 598400
4.1 | Integration Management | 6 days | Wed 4/27/22 | Wed 5/4/22 |  |  | 3000
4.1.1 | Document Integration Management Process | 5 days | Wed 4/27/22 | Tue 5/3/22 | 3 | Project Manager,Assistant Project Management | 3000
4.1.2 | Approve Integration Management Process | 1 day | Wed 5/4/22 | Wed 5/4/22 | 6 | Sponsor | 0
4.2 | Scope Management | 5 days | Wed 4/27/22 | Tue 5/3/22 |  |  | 2400
4.2.1 | Document Project Scope Management | 4 days | Wed 4/27/22 | Mon 5/2/22 | 3 | Project Manager,Assistant Project Management | 2400
4.2.2 | Approve Project Scope Management | 1 day | Tue 5/3/22 | Tue 5/3/22 | 9 | Sponsor | 0
4.3 | Schedule Management | 6 days | Wed 4/27/22 | Wed 5/4/22 |  |  | 3000
4.3.1 | Document Project Schedule Management | 5 days | Wed 4/27/22 | Tue 5/3/22 | 3 | Project Manager,Assistant Project Management | 3000
4.3.2 | Approve Project Schedule Management | 1 day | Wed 5/4/22 | Wed 5/4/22 | 12 | Sponsor | 0
4.4 | Cost Management | 8 days | Wed 4/27/22 | Fri 5/6/22 |  |  | 507000
4.4.1 | Document Cost Management | 7 days | Wed 4/27/22 | Thu 5/5/22 | 3 | Project Manager,Assistant Project Management,Materials Manager | 7000
4.4.2 | Assign Contingency Reserve | 1 day | Wed 4/27/22 | Wed 4/27/22 | 3 | Project Manager,Contingency[$500,000.00] | 500000
4.4.3 | Approve Cost Management | 1 day | Fri 5/6/22 | Fri 5/6/22 | 15 | Sponsor | 0
4.5 | Quality Management | 4 days | Mon 5/9/22 | Thu 5/12/22 |  |  | 1800
4.5.1 | Document Quality Management Control Measures | 3 days | Mon 5/9/22 | Wed 5/11/22 | 17 | Project Manager,Assistant Project Management | 1800
4.5.2 | Approve Quality Management Control Measures | 1 day | Thu 5/12/22 | Thu 5/12/22 | 19 | Sponsor | 0
4.6 | Resource Management | 4 days | Thu 5/12/22 | Tue 5/17/22 |  |  | 3000
4.6.1 | Document Resource Management | 3 days | Thu 5/12/22 | Mon 5/16/22 | 19 | Project Manager,Assistant Project Management,Materials Manager | 3000
4.6.2 | Approve Resource Management | 1 day | Tue 5/17/22 | Tue 5/17/22 | 22 | Sponsor | 0
4.7 | Communication Management | 3 days | Thu 5/12/22 | Mon 5/16/22 |  |  | 1200
4.7.1 | Document Communication Management Plan | 2 days | Thu 5/12/22 | Fri 5/13/22 | 19 | Project Manager,Assistant Project Management | 1200
4.7.2 | Approve Communication Management Plan | 1 day | Mon 5/16/22 | Mon 5/16/22 | 25 | Sponsor | 0
4.8 | Risk Management | 24 days | Tue 5/17/22 | Fri 6/17/22 |  |  | 74400
4.8.1 | Identifiation | 11 days | Tue 5/17/22 | Tue 5/31/22 |  |  | 68400
4.8.1.1 | Brainstorm Risks | 10 days | Tue 5/17/22 | Mon 5/30/22 | 26 | Assistant Construction Manager,Assistant Project Management,Designer 1,Designer 2,Designer 3,Guestroom Construction Manager,Lobby Construction Manager,Materials Manager,Meeting Space Construction Manager,Project Manager | 62400
4.8.1.2 | Create Risk Register | 10 days | Tue 5/17/22 | Mon 5/30/22 | 29SS | Assistant Project Management,Project Manager | 6000
4.8.1.3 | Approve Risk Register | 1 day | Tue 5/31/22 | Tue 5/31/22 | 30 | Sponsor | 0
4.8.2 | Risk Analysis | 7 days | Wed 6/1/22 | Thu 6/9/22 |  |  | 3600
4.8.2.1 | Document Risk Analysis | 6 days | Wed 6/1/22 | Wed 6/8/22 | 31 | Assistant Project Management,Project Manager | 3600
4.8.2.2 | Approve Risk Analysis | 1 day | Thu 6/9/22 | Thu 6/9/22 | 33 | Sponsor | 0
4.8.3 | Risk Prioritization | 3 days | Fri 6/10/22 | Tue 6/14/22 |  |  | 1200
4.8.3.1 | Prioritze Risks | 2 days | Fri 6/10/22 | Mon 6/13/22 | 34 | Project Manager,Assistant Project Management,Sponsor | 1200
4.8.3.2 | Approve Risk Prioritization | 1 day | Tue 6/14/22 | Tue 6/14/22 | 36 | Sponsor | 0
4.8.4 | Risk Management Plan | 3 days | Wed 6/15/22 | Fri 6/17/22 |  |  | 1200
4.8.4.1 | Document Risk Management Plan | 2 days | Wed 6/15/22 | Thu 6/16/22 | 37 | Project Manager,Assistant Project Management | 1200
4.8.4.2 | Approve Risk Management Plan | 1 day | Fri 6/17/22 | Fri 6/17/22 | 39 | Sponsor | 0
4.9 | Procurement Management | 3 days | Mon 6/20/22 | Wed 6/22/22 |  |  | 2000
4.9.1 | Document Procurement Management Strategy | 2 days | Mon 6/20/22 | Tue 6/21/22 | 40 | Project Manager,Assistant Project Management,Materials Manager | 2000
4.9.2 | Approve Procurement Management Strategy | 1 day | Wed 6/22/22 | Wed 6/22/22 | 42 | Sponsor | 0
4.1 | Stakeholder Management | 2 days | Thu 6/23/22 | Fri 6/24/22 |  |  | 600
4.10.1 | Document Stakeholder Management Plan | 1 day | Thu 6/23/22 | Thu 6/23/22 | 43 | Project Manager,Assistant Project Management,Sponsor | 600
4.10.2 | Approve Stakeholder Management Plan | 1 day | Fri 6/24/22 | Fri 6/24/22 | 45 | Sponsor | 0
4.11 | Project Documentation Complete | 0 days | Fri 6/24/22 | Fri 6/24/22 | 46 |  | 0
5 | Research | 9 days | Mon 6/27/22 | Thu 7/7/22 |  |  | 11200
5.1 | Compset Research | 9 days | Mon 6/27/22 | Thu 7/7/22 |  |  | 5600
5.1.1 | Research Compset | 7 days | Mon 6/27/22 | Tue 7/5/22 | 47 | Compset Researcher | 5600
5.1.2 | Present Compset Research to Project Sponsor | 1 day | Wed 7/6/22 | Wed 7/6/22 | 50 | Project Manager | 0
5.1.3 | Approve Compset Research | 1 day | Thu 7/7/22 | Thu 7/7/22 | 51 | Sponsor | 0
5.1.4 | Compset Research Complete | 0 days | Thu 7/7/22 | Thu 7/7/22 | 52 |  | 0
5.2 | Current Location Research | 9 days | Mon 6/27/22 | Thu 7/7/22 |  |  | 5600
5.2.1 | Research Current Location of Hotel to Determine Design Aesthetic | 7 days | Mon 6/27/22 | Tue 7/5/22 | 47 | Local Researcher | 5600
5.2.2 | Present Current Location Research to Project Sponsor | 1 day | Wed 7/6/22 | Wed 7/6/22 | 55 | Project Manager | 0
5.2.3 | Approve Current Location Research | 1 day | Thu 7/7/22 | Thu 7/7/22 | 56 | Sponsor | 0
5.2.4 | Current Location Research Complete | 0 days | Thu 7/7/22 | Thu 7/7/22 | 57 |  | 0
5.3 | Research Complete | 0 days | Thu 7/7/22 | Thu 7/7/22 | 58 |  | 0
6 | Design | 8 days | Fri 7/8/22 | Tue 7/19/22 |  |  | 14400
6.1 | Design Option 1 | 6 days | Fri 7/8/22 | Fri 7/15/22 |  |  | 4800
6.1.1 | Create Guestroom Design 1 | 2 days | Fri 7/8/22 | Mon 7/11/22 | 59 | Designer 1 | 1600
6.1.2 | Create Lobby Design 1 | 2 days | Tue 7/12/22 | Wed 7/13/22 | 62 | Designer 1 | 1600
6.1.3 | Create Meeting Space Design 1 | 2 days | Thu 7/14/22 | Fri 7/15/22 | 63 | Designer 1 | 1600
6.2 | Design Option 2 | 6 days | Fri 7/8/22 | Fri 7/15/22 |  |  | 4800
6.2.1 | Create Guestroom Design 2 | 2 days | Fri 7/8/22 | Mon 7/11/22 | 59 | Designer 2 | 1600
6.2.2 | Create Lobby Design 2 | 2 days | Tue 7/12/22 | Wed 7/13/22 | 66 | Designer 2 | 1600
6.2.3 | Create Meeting Space Design 2 | 2 days | Thu 7/14/22 | Fri 7/15/22 | 67 | Designer 2 | 1600
6.3 | Design Option 3 | 6 days | Fri 7/8/22 | Fri 7/15/22 |  |  | 4800
6.3.1 | Create Guestroom Design 3 | 2 days | Fri 7/8/22 | Mon 7/11/22 | 59 | Designer 3 | 1600
6.3.2 | Create Lobby Design 3 | 2 days | Tue 7/12/22 | Wed 7/13/22 | 70 | Designer 3 | 1600
6.3.3 | Create Meeting Space Design 3 | 2 days | Thu 7/14/22 | Fri 7/15/22 | 71 | Designer 3 | 1600
6.4 | Present Design Options to Project Sponsor | 1 day | Mon 7/18/22 | Mon 7/18/22 | 72 | Project Manager | 0
6.5 | Receive Sponsor Approval on Design Option 2 | 1 day | Tue 7/19/22 | Tue 7/19/22 | 73 | Sponsor | 0
6.6 | Design Complete | 0 days | Tue 7/19/22 | Tue 7/19/22 | 74 |  | 0
7 | Refurbishment | 359 days | Wed 7/20/22 | Mon 12/4/23 |  |  | 4189800
7.1 | Apply for Construction Permits | 2 days | Wed 7/20/22 | Thu 7/21/22 | 75 | Project Manager | 0
7.2 | Construction Permits Received | 0 days | Thu 7/21/22 | Thu 7/21/22 | 77 | Project Manager | 0
7.3 | Order Materials for Design Option 2 | 5 days | Wed 7/20/22 | Tue 7/26/22 | 75 | Project Manager,Materials Manager | 2000
7.4 | Guestroom Refurbishment | 290 days | Wed 7/27/22 | Tue 9/5/23 |  |  | 2417400
7.4.1 | Coordinate with Hotel Operations Staff to Shut Down Three Guestroom Floors at a Time for Refurbishment | 3 days | Wed 7/27/22 | Fri 7/29/22 | 79 | Project Manager,Assistant Project Management | 1800
7.4.2 | Demo Guestrooms on Top Floor | 5 days | Mon 8/1/22 | Fri 8/5/22 | 81 | Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Assistant Construction Manager | 11000
7.4.3 | Refurbish Guestrooms on Top Floor | 20 days | Mon 8/8/22 | Fri 9/2/22 | 82 | Guestroom Materials[0.09],Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Materials Manager,Assistant Construction Manager,Assistant Project Management | 208000
7.4.4 | Receive Approval on Top Floor Guestrooms | 1 day | Mon 9/5/22 | Mon 9/5/22 | 83 | Sponsor | 0
7.4.5 | Receive Inspection Sign Off on Top Floor Guestrooms | 1 day | Tue 9/6/22 | Tue 9/6/22 | 84 | Project Manager,Assistant Project Management | 600
7.4.6 | Demo Guestrooms on 11th Floor | 5 days | Tue 9/6/22 | Mon 9/12/22 | 84 | Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Assistant Construction Manager | 11000
7.4.7 | Refurbish Guestrooms on | 20 days | Tue 9/13/22 | Mon 10/10/22 | 86 | Guestroom Materials[0.09],Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Materials Manager,Assistant Construction Manager,Assistant Project Management | 208000
7.4.8 | Receive Approval on 11th Floor Guestrooms | 1 day | Tue 10/11/22 | Tue 10/11/22 | 87 | Sponsor | 0
7.4.9 | Receive Inspection Sign Off on 11th Floor Guestrooms | 1 day | Wed 10/12/22 | Wed 10/12/22 | 88 | Project Manager,Assistant Project Management | 600
7.4.10 | Demo Guestrooms on 10th Floor | 5 days | Wed 10/12/22 | Tue 10/18/22 | 88 | Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Assistant Construction Manager | 11000
7.4.11 | Refurbish Guestrooms on 10th Floor | 20 days | Wed 10/19/22 | Tue 11/15/22 | 90 | Guestroom Materials[0.09],Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Materials Manager,Assistant Construction Manager,Assistant Project Management | 208000
7.4.12 | Receive Approval on 10th Floor Guestrooms | 1 day | Wed 11/16/22 | Wed 11/16/22 | 91 | Sponsor | 0
7.4.13 | Receive Inspection Sign Off on 10th Floor Guestrooms | 1 day | Thu 11/17/22 | Thu 11/17/22 | 92 | Project Manager,Assistant Project Management | 600
7.4.14 | Demo Guestrooms on 9th Floor | 5 days | Thu 11/17/22 | Wed 11/23/22 | 92 | Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Assistant Construction Manager | 11000
7.4.15 | Refurbish Guestrooms on 9th Floor | 20 days | Thu 11/24/22 | Wed 12/21/22 | 94 | Guestroom Materials[0.09],Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Materials Manager,Assistant Construction Manager,Assistant Project Management | 208000
7.4.16 | Receive Approval on 9th Floor Guestrooms | 1 day | Thu 12/22/22 | Thu 12/22/22 | 95 | Sponsor | 0
7.4.17 | Receive Inspection Sign Off on 9th Floor Guestrooms | 1 day | Fri 12/23/22 | Fri 12/23/22 | 96 | Project Manager,Assistant Project Management | 600
7.4.18 | Demo Guestrooms on 8th Floor | 5 days | Fri 12/23/22 | Thu 12/29/22 | 96 | Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Assistant Construction Manager | 11000
7.4.19 | Refurbish Guestrooms on 8th Floor | 20 days | Fri 12/30/22 | Thu 1/26/23 | 98 | Guestroom Materials[0.09],Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Materials Manager,Assistant Construction Manager,Assistant Project Management | 208000
7.4.20 | Receive Approval on 8th Floor Guestrooms | 1 day | Fri 1/27/23 | Fri 1/27/23 | 99 | Sponsor | 0
7.4.21 | Receive Inspection Sign Off on 8th Floor Guestrooms | 1 day | Mon 1/30/23 | Mon 1/30/23 | 100 | Project Manager,Assistant Project Management | 600
7.4.22 | Demo Guestrooms on 7th Floor | 5 days | Mon 1/30/23 | Fri 2/3/23 | 100 | Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Assistant Construction Manager | 11000
7.4.23 | Refurbish Guestrooms on 7th Floor | 20 days | Mon 2/6/23 | Fri 3/3/23 | 102 | Guestroom Materials[0.09],Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Materials Manager,Assistant Construction Manager,Assistant Project Management | 208000
7.4.24 | Receive Approval on 7th Floor Guestrooms | 1 day | Mon 3/6/23 | Mon 3/6/23 | 103 | Sponsor | 0
7.4.25 | Receive Inspection Sign Off on 7th Floor Guestrooms | 1 day | Tue 3/7/23 | Tue 3/7/23 | 104 | Project Manager,Assistant Project Management | 600
7.4.26 | Demo Guestrooms on 6th Floor | 5 days | Tue 3/7/23 | Mon 3/13/23 | 104 | Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Assistant Construction Manager | 11000
7.4.27 | Refurbish Guestrooms on 6th Floor | 20 days | Tue 3/14/23 | Mon 4/10/23 | 106 | Guestroom Materials[0.09],Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Materials Manager,Assistant Construction Manager,Assistant Project Management | 208000
7.4.28 | Receive Approval on 6th Floor Guestrooms | 1 day | Tue 4/11/23 | Tue 4/11/23 | 107 | Sponsor | 0
7.4.29 | Receive Inspection Sign Off on 6th Floor Guestrooms | 1 day | Wed 4/12/23 | Wed 4/12/23 | 108 | Project Manager,Assistant Project Management | 600
7.4.30 | Demo Guestrooms on 5th Floor | 5 days | Wed 4/12/23 | Tue 4/18/23 | 108 | Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Assistant Construction Manager | 11000
7.4.31 | Refurbish Guestrooms on 5th Floor | 20 days | Wed 4/19/23 | Tue 5/16/23 | 110 | Guestroom Materials[0.09],Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Materials Manager,Assistant Construction Manager,Assistant Project Management | 208000
7.4.32 | Receive Approval on 5th Floor Guestrooms | 1 day | Wed 5/17/23 | Wed 5/17/23 | 111 | Sponsor | 0
7.4.33 | Receive Inspection Sign Off on 5th Floor Guestrooms | 1 day | Thu 5/18/23 | Thu 5/18/23 | 112 | Project Manager,Assistant Project Management | 600
7.4.34 | Demo Guestrooms on 4th Floor | 5 days | Thu 5/18/23 | Wed 5/24/23 | 112 | Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Assistant Construction Manager | 11000
7.4.35 | Refurbish Guestrooms on 4th Floor | 20 days | Thu 5/25/23 | Wed 6/21/23 | 114 | Guestroom Materials[0.09],Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Materials Manager,Assistant Construction Manager,Assistant Project Management | 208000
7.4.36 | Receive Approval on 4th Floor Guestrooms | 1 day | Thu 6/22/23 | Thu 6/22/23 | 115 | Sponsor | 0
7.4.37 | Receive Inspection Sign Off on 4th Floor Guestrooms | 1 day | Fri 6/23/23 | Fri 6/23/23 | 116 | Project Manager,Assistant Project Management | 600
7.4.38 | Demo Guestrooms on 3rd Floor | 5 days | Fri 6/23/23 | Thu 6/29/23 | 116 | Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Assistant Construction Manager | 11000
7.4.39 | Refurbish Guestrooms on 3rd Floor | 20 days | Fri 6/30/23 | Thu 7/27/23 | 118 | Guestroom Materials[0.09],Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Materials Manager,Assistant Construction Manager,Assistant Project Management | 208000
7.4.40 | Receive Approval on 3rd Floor Guestrooms | 1 day | Fri 7/28/23 | Fri 7/28/23 | 119 | Sponsor | 0
7.4.41 | Receive Inspection Sign Off on 3rd Floor Guestrooms | 1 day | Mon 7/31/23 | Mon 7/31/23 | 120 | Project Manager,Assistant Project Management | 600
7.4.42 | Demo Guestrooms on 2nd Floor | 5 days | Mon 7/31/23 | Fri 8/4/23 | 120 | Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Assistant Construction Manager | 11000
7.4.43 | Refurbish Guestrooms on 2nd Floor | 20 days | Mon 8/7/23 | Fri 9/1/23 | 122 | Guestroom Materials[0.09],Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Guestroom Construction Manager,Materials Manager,Assistant Construction Manager,Assistant Project Management | 208000
7.4.44 | Receive Approval on 2nd Floor Guestrooms | 1 day | Mon 9/4/23 | Mon 9/4/23 | 123 | Sponsor | 0
7.4.45 | Receive Inspection Sign Off on 2nd Floor Guestrooms | 1 day | Tue 9/5/23 | Tue 9/5/23 | 124 | Project Manager,Assistant Project Management | 600
7.4.46 | Guestroom Refurbishment Complete | 0 days | Mon 9/4/23 | Mon 9/4/23 | 124 |  | 0
7.5 | Lobby Refurbishment | 62 days | Tue 9/5/23 | Wed 11/29/23 |  |  | 684000
7.5.1 | Demo Lobby | 20 days | Tue 9/5/23 | Mon 10/2/23 | 126 | Assistant Construction Manager,Assistant Project Management,Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Lobby Construction Manager | 56000
7.5.2 | Refurbish Lobby | 40 days | Tue 10/3/23 | Mon 11/27/23 | 128 | Lobby Materials[1],Assistant Construction Manager,Assistant Project Management,Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Lobby Construction Manager,Materials Manager | 628000
7.5.3 | Receive Approval on Lobby Refurbishment | 1 day | Tue 11/28/23 | Tue 11/28/23 | 129 | Sponsor | 0
7.5.4 | Receive Inspection Sign Off on Lobby | 1 day | Wed 11/29/23 | Wed 11/29/23 | 130 | Project Manager | 0
7.5.5 | Lobby Refurbishment Complete | 0 days | Tue 11/28/23 | Tue 11/28/23 | 130 | Project Manager | 0
7.6 | Meeting Space Refurbishment | 65 days | Tue 9/5/23 | Mon 12/4/23 |  |  | 1086400
7.6.1 | Coordinate with Sales Team to Ensure No Events/Meetings Occuring in the Space | 3 days | Tue 9/5/23 | Thu 9/7/23 | 126 | Project Manager,Assistant Project Management | 1800
7.6.2 | Demo Meeting Space | 20 days | Fri 9/8/23 | Thu 10/5/23 | 134 | Assistant Construction Manager,Assistant Project Management,Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Meeting Space Construction Manager | 56000
7.6.3 | Refurbish Meeting Space | 40 days | Fri 10/6/23 | Thu 11/30/23 | 135 | Meeting Space Materials[1],Assistant Construction Manager,Assistant Project Management,Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Meeting Space Construction Manager,Materials Manager | 1028000
7.6.4 | Receive Approval on Meeting Space Refurbishment | 1 day | Fri 12/1/23 | Fri 12/1/23 | 136 | Sponsor | 0
7.6.5 | Receive Inpsection Sign Off on Meeting Space | 1 day | Mon 12/4/23 | Mon 12/4/23 | 137 | Project Manager,Assistant Project Management | 600
7.6.6 | Meeting Space Refurbishment Complete | 0 days | Fri 12/1/23 | Fri 12/1/23 | 137 |  | 0
7.7 | Refurbishment Complete | 0 days | Fri 12/1/23 | Fri 12/1/23 | 139 |  | 0
8 | Sponsor Sign Off | 0 days | Fri 12/1/23 | Fri 12/1/23 | 140 | Sponsor | 0
9 | Lessons Learned | 4 days | Mon 12/4/23 | Thu 12/7/23 |  |  | 23520
9.1 | Host Meeting | 1 day | Mon 12/4/23 | Mon 12/4/23 | 141 | Project Manager | 0
9.2 | Document Lessons Learned | 3 days | Tue 12/5/23 | Thu 12/7/23 | 143 | Project Manager,Assistant Construction Manager,Assistant Project Management,Compset Researcher,Designer 1,Designer 2,Designer 3,Guestroom Construction Manager,Lobby Construction Manager,Local Researcher,Materials Manager,Meeting Space Construction Mana... | 23520
9.3 | Lessons Learned Complete | 0 days | Thu 12/7/23 | Thu 12/7/23 | 144 |  | 0
10 | Host Meeting to Celebrate Project Completion with Project Team | 4 days | Fri 12/8/23 | Wed 12/13/23 | 145 | Project Manager,Assistant Construction Manager,Assistant Project Management,Compset Researcher,Construction Worker 1,Construction Worker 2,Construction Worker 3,Construction Worker 4,Designer 1,Designer 2,Designer 3,Guestroom Construction Manager,Lobby... | 39200
11 | Close Cost Accounts | 1 day | Thu 12/14/23 | Thu 12/14/23 | 146 | Project Manager,Assistant Project Management | 600
12 | Close Project | 1 day | Fri 12/15/23 | Fri 12/15/23 | 147 | Project Manager,Assistant Project Management | 600
13 | Project Complete | 0 days | Fri 12/15/23 | Fri 12/15/23 | 148 |  | 0